## Sheet1
Sl No. | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund received in 2016 | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status | Fund lapsed | Revalidation required | Pending UC | Reallocation proposed | Refund to be proposed | Reallocation to be done | Reallocated | Drawn | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Narsingarh H. S. School, Agartala, West Tripura | THCB | 37 | 0 | 20 | 17 | 750 | 800 | 800 | Brownfield | 150 | SPA | 2013-14 | 150 | 32.5 | 117.5 | 461.91 | 177.81 | 117.5 | Structural work completed in 1st floor | 0 | 0 | 0 | 0 | 0 | 32.5 | 0 | 0
2 | Lankamura H. S. School, Agartala, West Tripura | THCB | 28 | 4 | 12 | 12 | 1000 | 1000 | 100 | Brownfield | 100 | SCA untied | 2014-15 | 100 | 0 | 100 |  | 18.91 | 0 | Dismantling work is completed | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
3 | Bani Vidyapith Girls H. S. School, Agartala, West Tripura | THCB | 35 | 22 | 10 | 3 | 938.43 | 938 | 938 | Brownfield | 562.5 | SPA | 2008-09 | 562.5 | 0 | 562.5 | 780.16 | 562.5 | 562.5 | Major part of the building raised upto roof level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Bani Vidyapith Girls H. S. School, Agartala, West Tripura | THCB | 35 | 22 | 10 | 3 |  |  |  | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 |  | 180 | 180 | Major part of the building raised upto roof level. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
5 | Bani Vidyapith Girls H. S. School, Agartala, West Tripura | THCB | 35 | 22 | 10 | 3 |  |  |  | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 |  | 100 | 100 | Major part of the building raised upto roof level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 707.69 | 707.69 | 707.69 | Greenfield | 707.69 | SDS | 2015-16 | 707.69 | 0 | 0 | 232.34 | 0 | 0 | Finishing Work is in progress in the Eastern part and pilling work is in progress in the western part | 707.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 500 | 500 | 500 | Greenfield | 500 | SPA | 2010-11 | 500 | 0 | 500 | 417.2 | 600.48 | 500 | Finishing Work is in progress in the Eastern part and pilling work is in progress in the western part | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 46.44 | 46.44 | 46.44 | Greenfield | 46.44 | SDS | 2015-16 | 46.44 | 0 | 0 | 26 | 0 | 0 | Work in progress | 46.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 50 | 50 | 50 | Greenfield | 50 | SPA | 2013-14 | 50 | 0 | 50 | 45 | 45 | 45 | Completed | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
10 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 | 815 | 65.11 | 65.11 | Brownfield | 65.11 | SDS | 2016-17 | 0 | 0 | 0 | 485.29 | 187.5 | 0 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 |  | 25 | 25 | Brownfield | 25 | SCA | 2013-14 | 12.5 | 0 | 12.5 |  | 12.5 | 12.5 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 |  | 100 | 100 | Brownfield | 100 | SCA | 2011-12 | 100 | 0 | 100 |  | 100 | 100 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 |  | 300 | 270 | Brownfield | 300 | SPA | 2012-13 | 300 | 30 | 270 |  | 270 | 270 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0
14 | Ramthakur Pathshala Girls H.S. School, Agartala, West Tripura | THCB | 27 | 28 | 0 | -1 | 717 | 250 | 250 | Brownfield | 250 | SPA | 2012-13 | 250 | 0 | 250 | 484.87 | 380.87 | 225 | Structural work Completed. | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0
15 | Ramthakur Pathshala Girls H.S. School, Agartala, West Tripura | THCB | 27 | 28 | 0 | -1 |  | 280 | 280 | Brownfield | 280 | SPA | 2013-14 | 252 | 0 | 252 | 10.47 | 252 | 252 | Structural work Completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Ramthakur Pathshala Boys H.S. School, Agartala, West Tripura | THCB | 22 | 1 | 24 | -3 | 750 | 750 | 750 | Brownfield | 30 | SCA | 2013-14 | 15 | 0 | 15 | 478.9 | 52.53 | 15 | Finishing work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Ramthakur Pathshala Boys H.S. School, Agartala, West Tripura | THCB | 22 | 1 | 24 | -3 |  |  |  | Brownfield | 300 | SPA | 2012-13 | 300 | 0 | 300 | 0 | 300 | 270 | Finishing work is in progress | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0
18 | Ramthakur Pathshala Boys H.S. School, Agartala, West Tripura | THCB | 22 | 1 | 24 | -3 |  |  |  | Brownfield | 100 | SCA | 2011-12 | 100 | 0 | 100 |  | 100 | 100 | Finishing work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Kamini Kumar Singha Memorial H.S. School, Agartala, West Tripura | THCB | 38 | 8 | 20 | 10 | 550 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 355.84 | 266.7 | 97.5 | Plastering work is going on. | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0
20 | Kabiraj Tilla H.S. School, Agartala, West Tripura | THCB | 26 | 0 | 32 | -6 | 1987 | 200 | 200 | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 457.38 | 0.482 | 0 | Column raised upto roof level in under ground floor. | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0
21 | Office Tilla H.S. School, Bishalgarh, West Tripura | THCB | 36 | 0 | 41 | -5 | 900 | 900 | 400 | Brownfield | 100 | SPA | 2013-14 | 85 | 0 | 85 | 452.59 | 85 | 85 | GF roof custing completed, Brickwork and plastering is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Office Tilla H.S. School, Bishalgarh, West Tripura | THCB | 36 | 0 | 41 | -5 |  |  |  | Brownfield | 800 | Niti Aayog | 2015-16 | 300 | 300 | 0 |  | 214.65 | 0 | Work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0
23 | Sakhicharan H.S. School, Agartala, West Tripura | THCB | 25 | 0 | 29 | -4 | 1529.97 | 100 | 100 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 476.31 | 30 | 30 | Temporary Structure Completed and dismentling work will be started after Durga Puja. | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0
24 | Bishalgarh Town Girls High School, Bishalgarh, West Tripura | THCB | 21 | 0 | 40 | -19 | 400 | 400 | 200 | Brownfield | 200 | SDS | 2015-16 | 200 | 200 | 0 | 314.71 | 0.72 | 0 | Dismantling Completed and clear site handover to THCB | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
25 | Golaghati High School, Bishalgarh, West Tripura | THCB | 21 | 0 | 25 | -4 | 580.78 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 280.51 | 100 | 90 | Finishing work is in progress in 1st phase and work order issued for 2nd phase of the work | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
26 | Golaghati High School, Bishalgarh, West Tripura | THCB | 21 | 0 | 25 | -4 |  | 481 | 481 | Brownfield | 481 | Niti Ayog | 2015-16 | 240.5 | 240.5 | 0 |  | 108.38 | 0 | Finishing work is in progress in 1st phase and work order issued for 2nd phase of the work | 0 | 0 | 0 | 0 | 0 | 0 | 240.5 | 0
27 | Baidyar Dighi H.S. School, Bishalgarh, West Tripura | THCB | 30 | 4 | 21 | 5 | 700 | 700 | 100 | Brownfield | 100 | SPA | 2013-14 | 80 | 0 | 80 | 471.6 | 80 | 80 | Work raised upto P.L. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Khowai Girls H.S. School, Khowai Tripura | THCB | 34 | 11 | 39 | -16 | 1000 | 1000 | 1000 | brownfield | 200 | SPA | 2013-14 | 90 | 0 | 90 | 478.49 | 90 | 90 | Structural work completed, brick wall and finishing work in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Khowai Girls H.S. School, Khowai Tripura | THCB | 34 | 11 | 39 | -16 |  |  |  | brownfield | 800 | Niti Aayog | 2015-16 | 300 | 300 | 0 |  | 321.68 | 0 | Structural work completed, brick wall and finishing work in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0
30 | Pallimangal H.S. School, West Tripura | THCB | 35 | 12 | 17 | 6 | 958 | 958 | 958 | brownfield | 500 | SPA | 2010-11 | 450 | 0 | 450 | 420.83 | 450 | 450 | First phase of work is completed & handed over. In second phase, brick and finishing work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Pallimangal H.S. School, West Tripura | THCB | 35 | 12 | 17 | 6 |  |  |  | brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 378.73 | 230.64 | 180 | First phase of work is completed & handed over. In second phase, brick and finishing work in progress | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
32 | Vidyasagar High School, West Tripura | THCB | 21 | 0 | 19 | 2 | 567.5 | 567.5 | 567.5 | brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 239.16 | 45 | 45 | 50% building reached upto plinth level. | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0
33 | Champaknagar H.S. School, West Tripura | THCB | 29 | 0 | 21 | 8 | 1405.93 | 1405 | 1405 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 450.715 | 0.18 | 0 | Work to be started soon. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
34 | Barjala Binapani H.S. School, West Tripura | THCB | 29 | 3 | 18 | 8 | 1311.18 | 1311 | 1311 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 464.64 | 100 | 100 | Raised upto plinth level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | Ranir Goan H.S. School, West Tripura | THCB | 31 | 10 | 20 | 1 | 1732.93 | 1732 | 1732 | brownfield | 155.4 | SCA | 2014-15 | 100 | 0 | 100 | 488.5 | 6.73 | 0 | Work order issued. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
36 | Sankaracharyya Vidyaniketan, West Tripura | THCB | 27 | 8 | 34 | -15 | 907 | 907 | 907 | brownfield | 462 | SPA | 2012-13 | 415.8 | 0 | 415.8 | 409.28 | 415.8 | 415.8 | 70% Structural work completed phase-I portion. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Bokafa H.S. School, South Tripura | THCB | 33 | 8 | 28 | -3 | 700 | 700 | 700 | brownfield | 100 | SPA | 2013-14 | 100 | 50 | 50 | 458.58 | 64.86 | 0 | Pilling is in progress. | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0
38 | Uttar Maheshpur S.B. School, Sepahijala Tripura | THCB | 17 | 0 | 12 | 5 | 232 | 100 | 100 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 184.78 | 145 | 100 | 40% GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Bhabanipur H.S. School, Sepahijala Tripura | THCB | 15 | 2 | 12 | 1 | 100 | 100 | 100 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 0 | 0 | 0 | Work is not required. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
40 | Nutan Nagar Girls H.S. School, Sepahijala Tripura | THCB | 26 | 26 |  | 0 | 750 | 750 | 750 | brownfield | 25 | SCA | 2013-14 | 12.5 | 0 | 12.5 | 366.48 | 12.5 | 12.5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Nutan Nagar Girls H.S. School, Sepahijala Tripura | THCB | 26 | 26 |  | 0 |  |  |  | brownfield | 300 | SPA | 2012-13 | 290 | 0 | 290 |  | 270 | 270 | Completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
42 | Nutan Nagar Girls H.S. School, Sepahijala Tripura | THCB | 26 | 26 |  | 0 |  |  |  | brownfield | 100 | SCA | 2011-12 | 100 | 0 | 100 |  | 100 | 100 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Bishramganj H.S. School, Sepahijala Tripura | THCB | 48 | 0 | 35 | 13 | 904 | 904 | 904 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 465.268 | 100 | 100 | GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Bishramganj H.S. School, Sepahijala Tripura | THCB | 48 | 0 | 35 | 13 |  |  |  | brownfield | 200 | SPA | 2013-14 | 180 | 0 | 180 |  | 180 | 180 | GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Bishramganj H.S. School, Sepahijala Tripura | THCB | 48 | 0 | 35 | 13 |  |  |  | brownfield | 439 | Niti Aayog | 2015-16 | 220 | 220 | 0 |  | 0 | 0 | GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0
46 | Rajnagar H.S. School, West Tripura | THCB | 25 | 0 | 18 | 7 | 397 | 397 | 397 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 424.68 | 121.83 | 100 | Pile work is in progress. Out of 193, 145 nos pile work completed. Arrangement is being made for load test. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Ramkrishna Ashram Vidyamandir High School, West Tripura | THCB | 29 | 0 | 22 | 7 | 794.72 | 520 | 520 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 293.57 | 13.34 | 0 | Dismantling work is going on. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
48 | Nidaya H.S. School, Sepahijala Tripura | THCB | 24 | 0 | 0 | 24 | 465 | 100 | 100 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 |  | 0 | 0 | 100 Lac sanctioned by P&C but project proposal of Rs.463.00 lacs send to P&C for getting sectioned. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
49 | Bodhjung Boys H.S. School, West Tripura | THCB | 35 | 0 | 22 | 13 | 1306 | 1306 | 1306 | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 447.8 | 392.89 | 180 | Structural work , B/W , plastering work in northen block is completed, 50% of foundaton work in westren block is completed. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
50 | Khowai English Medium H.S. School,Khowai Tripura | THCB | 25 | 0 | 19 | 6 | 1000 | 300 | 300 | Brownfield | 300 | SDS | 2015-16 | 300 | 0 | 300 | 315.44 | 100 | 100 | Foundation work is in progress | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0
51 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 350 | 350 | 350 | Brownfield | 350 | SPA | 2009-10 | 315 | 0 | 315 | 252.12 | 315 | 315 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 115 | 115 | 115 | Brownfield | 115 | SCA | 2011-12 | 115 | 0 | 115 | 115.02 | 115 | 115 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 200 | 200 | 200 | Brownfield | 200 | SPA | 2012-13 | 180 | 0 | 180 |  | 180 | 180 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 210 | 210 | 210 | Brownfield | 210 | SPA | 2013-14 | 189 | 0 | 189 |  | 189 | 189 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 135.61 | 135.61 | 135.61 | Brownfield | 135.61 | SDS | 2015-16 | 135.61 | 0 | 135.61 |  | 0 | 0 | In progress | 0 | 0 | 135.61 | 0 | 0 | 0 | 0 | 0
56 | M.G.M. H.S. School, WestTripura | THCB | 32 | 16 | 15 | 1 | 1049 | 1049 | 1049 | Brownfield | 250 | SPA | 2012-13 | 250 | 25 | 225 | 317.48 | 250 | 225 | Work of FF is in finishing stage, work of the main building in old premicess reached above PL. | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
57 | M.G.M. H.S. School, WestTripura | THCB | 32 | 16 | 15 | 1 | 1049 |  |  |  | 500 | SPA | 2009-10 | 450 | 0 | 450 | 432.03 | 450 | 450 | Work of FF is in finishing stage, work of the main building in old premicess reached above PL. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | M.G.M. H.S. School, WestTripura | THCB | 32 | 16 | 15 | 1 | 1049 |  |  | Brownfield | 187.5 | SPA | 2013-14 | 187.5 | 18.75 | 168.75 |  | 168.75 | 168.75 | Work of FF is in finishing stage, work of the main building in old premicess reached above PL. | 0 | 0 | 0 | 0 | 0 | 18.75 | 0 | 0
59 | Chandrapur Colony H.S. School, WestTripura | THCB | 30 | 10 | 38 | -18 | 800 | 800 | 800 | Brownfield | 150 | SPA | 2013-14 | 150 | 32.5 | 117.5 | 447.135 | 147.5 | 117.5 | 50% Structural part has been completed. | 0 | 0 | 0 | 0 | 0 | 32.5 | 0 | 0
60 | Kumari Madhuti Rupasree High School, Khowai Tripura | THCB | 21 | 0 | 22 | -1 | 416.95 | 450 | 225 | Greenfield | 450 | SDS | 2015-16 | 225 | 225 | 0 | 277.92 | 63 | 0 | Structural work raised upto PL. | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0
61 | Bishalgarh Class XII School, WestTripura | THCB | 43 | 30 | 0 | 13 | 920 | 520 | 520 | Brownfield | 520 | SPA | 2010-11 | 520 | 0 | 520 |  | 520 | 520 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | Bishalgarh Class XII School, WestTripura | THCB | 43 | 30 | 0 | 13 |  | 400 | 200 | Brownfield | 400 | SDS | 2015-16 | 200 | 200 | 0 |  | 10.64 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
63 | Ranir Bazar H.S. School, West Tripura | THCB | 39 | 59 | 0 | -20 | 600 | 600 | 100 | brownfield | 100 | SCA | 2013-14 | 100 | 0 | 100 | 499.94 | 419.95 | 100 | Completed and handed over. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | AD Nagar Eng.Med. H.S. School, West Tripura | THCB | 29 | 0 | 34 | -5 | 1064 | 1064 | 1064 | Greenfield | 100 | SPA | 2013-14 | 45 | 0 | 45 | 451.409 | 211.37 | 45 | Slab casting for FF roof in !st block completed upto expansion joint. Reinforcement binding for PB in north west block is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | Subhas Nagar H.S. School, West Tripura | THCB | 25 | 0 | 21 | 4 | 724 | 724 | 724 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 392.97 | 0 | 0 | Work order issued, auction tender invited for dismantling old structure. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
66 | Construction of Ramnagar Girls' High School. | THCB | NA | NA | NA | NA | 40 | 40 | 40 | Brownfield | 40 | SCA | 2012-13 | 40 | 0 | 40 | 40 | 40 | 40 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | Construction of Karaimura H. S. School. | THCB | NA | NA | NA | NA | 52 | 52 | 52 | Brownfield | 52 | SCA | 2012-13 | 52 | 0 | 52 | 52 | 52 | 0 | Completed | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0
68 | Construction of Sahid Bhagat Singh Hindi Medium School (Phase-I). | THCB | NA | NA | NA | NA | 350 | 350 | 350 | Brownfield | 350 | SPA | 2009-10 | 315 | 0 | 315 |  | 315 | 311.69 | Completed | 0 | 0 | 3.31 | 0 | 0 | 0 | 0 | 0
69 | Construction of Sahid Bhagat Singh Hindi Medium School (Phase-II). | THCB | NA | NA | NA | NA | 35 | 35 | 35 | Brownfield | 35 | SCA | 2012-13 | 35 | 0 | 35 | 35 | 35 | 0 | Completed | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0
70 | Construction of Nabagram H. S. School. | THCB | 0 | 0 | 0 | 0 | 772 | 772 | 772 | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 722 | 390.73 | 90 | Completed | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
71 | Upgradation of infrastructure of Kalyanpur HS School | THCB | 0 | 0 | 0 | 0 | 500 | 500 | 250 | Brownfield | 500 | SDS | 2015-16 | 250 | 250 | 0 |  | 1 | 0 | Work order issued | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0
72 | Ram Krishna Vivekananda Vidyalaya, Agartala | THCB | 0 | 0 | 0 | 0 | 724 | 724 | 724 | Brownfield | 100 | SDS | 2016-17 | 0 | 0 | 0 |  | 0 | 0 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | Dr. B.R Ambedkar High School, Agartala | THCB | 0 | 0 | 0 | 0 | 520 | 520 | 520 | Brownfield | 520 | SPA | 2008-09 | 468.5 | 0 | 468.5 | 437.42 | 325.38 | 325.38 | Completed | 0 | 0 | 143.12 | 0 | 0 | 0 | 0 | 0
74 | Dr. B.R Ambedkar High School, Agartala | THCB | 0 | 0 | 0 | 0 | 218 | 218 | 218 | Brownfield | 218 | SPA | 2012-13 | 218 | 0 | 218 |  | 119.9 | 119.9 | Completed | 0 | 0 | 98.1 | 0 | 0 | 0 | 0 | 0
75 | Auditorium at St Paul's HS School Agartala | THCB | NA | NA | NA | NA | 461 | 461 | 461 | Greenfield | 150 | SPA | 2012-13 | 135 | 0 | 135 | 307.72 | 0.27 | 0 | Work started | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0
76 | Auditorium at St Paul's HS School Agartala | THCB | NA | NA | NA | NA |  |  |  | Greenfield | 150 | SPA | 2013-14 | 75 | 0 | 75 |  | 0 | 0 | Work started | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0
77 | Bardowali HS School | THCB | 0 | 0 | 0 | 0 | 900 | 900 | 830 | Brownfield | 500 | SPA | 2009-10 | 450 | 0 | 450 |  | 600.62 | 450 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Bardowali HS School | THCB | 0 | 0 | 0 | 0 |  |  |  | Brownfield | 200 | SPA | 2012-13 | 200 | 20 | 180 |  | 180 | 180 | Completed | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0
79 | Bardowali HS School | THCB | 0 | 0 | 0 | 0 |  |  |  | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 |  | 200 | 170 | In progress | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0
80 | Kirit Bikram Institute(KBI),Udaipur (PhaseI) | PWD | NA | NA | NA | NA | 400 | 400 | 400 | Brownfield | 400 | SPA | 2009-10 | 360 | 0 | 360 |  | 360 | 235 | Completed and handed over. | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0
81 | Bijoy Kumar Girls H. S. School, Agartala, West Tripura | PWD | 33 | 8 | 23 | 2 | 874 | 874 | 680 | Brownfield | 200 | SPA | 2012-13 | 200 | 0 | 200 | 640.84 | 180 | 145 | GF work 70% completed, FF work 50% completed and foundation work of remaining part 75% completed | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0
82 | Bijoy Kumar Girls H. S. School, Agartala, West Tripura | PWD | 33 | 8 | 23 | 2 |  |  |  | Brownfield | 99 | SPA | 2013-14 | 85 | 0 | 85 |  | 65 | 65 | GF work 70% completed, FF work 50% completed and foundation work of remaining part 75% completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
83 | Bijoy Kumar Girls H. S. School, Agartala, West Tripura | PWD | 33 | 8 | 23 | 2 |  |  |  | Brownfield | 390 | Niti Aayog | 2015-16 | 195 | 195 | 195 |  | 195 | 195 | GF work 70% completed, FF work 50% completed and foundation work of remaining part 75% completed | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 195
84 | Netaji Subhash Vidyaniketan, Agartala, West Tripura(Phase III) | PWD | 43 | 21 | 19 | 3 | 840 | 840 | 840 | Brownfield | 840 | SPA | 2014-15 | 500 | 300 | 200 | 538.92 | 200 | 200 | Dismantling Work complete. | 0 | 0 | 0 | 0 | 200 | 100 | 0 | 0
85 | Upgradation of infrastructure of NSV under ACA/Phase-II | PWD | 43 | 21 | 19 | 3 | 263.76 | 300 | 300 | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 100 | 100 | 100 | Work Completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Earth filling at the back side water bodies at NSV and Construction of boundary wall. | PWD | NA | NA | NA | NA | 50 | 25 | 25 | Brownfield | 25 | SCA | 2013-14 | 25 | 0 | 25 | 25 | 25 | 25 | Work Almost Completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Upgradation of infrastructure of NSV etc. Dev. Playground with drainage facilities and installation of one befitting entrance gate at mid section, Construction of storm water drainage. | PWD | NA | NA | NA | NA | 233 | 233 | 233 | Brownfield | 233 | SDS | 2015-16 | 233 | 0 | 233 | 233 | 233 | 233 | 3nos. Work order issued. Earth work in field in progress. Other works not yet started. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Upgradation of Infrastructure of boundary wall, site development & internal road with dranage system of Shishu Bihar School, Agartala, West Tripura | PWD | NA | NA | NA | NA | 100 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 90 | 12 | 78 |  | 78 | 50 | Completed | 0 | 0 | 28 | 0 | 0 | 12 | 0 | 0
89 | Baghan H.S. School, North Tripura | PWD | 25 | 10 | 33 | -18 | 500 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 |  | 90 | 90 | DNIT under preperation by PWD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Baghan H.S. School, North Tripura | PWD | 25 | 10 | 33 | -18 |  |  |  | Brownfield | 400 | Niti Aayog | 2015-16 | 100 | 100 | 0 |  | 0 | 0 | DNIT under preperation by PWD | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
91 | Dharmanagar Girls H.S. School, North Tripura | PWD | 25 | 28 | 0 | 11 | 450 | 450 | 450 | Brownfield | 213 | SPA | 2006-07 | 191.7 | 0 | 191.7 |  | 191.7 | 175 | Completed | 0 | 0 | 16.7 | 0 | 0 | 0 | 0 | 0
92 | Dharmanagar Girls H.S. School, North Tripura (PhaseII) | PWD | 39 | 28 | 0 | 11 |  |  |  | Brownfield | 450 | SPA | 2012-13 | 450 | 0 | 450 |  | 405 | 298.19 | Completed | 0 | 0 | 151.81 | 0 | 0 | 0 | 0 | 0
93 | Dharmanagar Boys H.S. School,(BBI)(Phase II) | PWD | 39 | 28 | 0 | 11 | 248 | 248 | 248 | Brownfield | 248 | SPA | 2007-08 | 223.2 | 0 | 223.2 |  | 223.2 | 188.64 | Completed | 0 | 0 | 34.56 | 0 | 0 | 0 | 0 | 0
94 | Kanchanpur H.S. School, North Tripura | PWD | 34 | 32 | 0 | 2 | 400 | 400 | 400 | Brownfield | 400 | SPA | 2008-09 | 360 | 0 | 59.8 |  | 360 | 59.8 | Completed | 300.2 | 300.2 | 0 | 0 | 0 | 0 | 0 | 0
95 | Chawmanu H.S. School, Dhalai Tripura | PWD | 37 | 10 | 8 | 19 | 600 | 222.35 | 45 | Brownfield | 90 | SPA | 2013-14 | 45 | 0 | 45 |  | 0 | 0 | Work order issued, existing structure demolished,foundation work started | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0
96 | Chawmanu H.S. School, Dhalai Tripura | PWD | 37 | 10 | 8 | 19 |  | 500 | 150 | Brownfield | 500 | Niti Aayog | 2015-16 | 150 | 150 | 0 |  | 0 | 0 | Work order issued, existing structure demolished,foundation work started | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
97 | Anandabazar H.S. School, North Tripura | PWD | 31 | 10 | 27 | -6 | 720 | 720 | 90 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 |  | 90 | 90 | Tender under scrutiny | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Anandabazar H.S. School, North Tripura | PWD | 31 | 10 | 27 | -6 |  |  |  | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 |  | 0 | 0 | Tender under scrutiny | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
99 | Srirampur Suryamani M. H.S. School, Unakoti Tripura | PWD | 32 | 6 | 16 | 10 | 438 | 300 | 300 | brownfield | 300 | SDS | 2015-16 | 300 | 300 | 0 | 262.25 | 0 | 0 | Work order issued. | 0 | 0 | 0 | 200 | 100 | 0 | 0 | 0
100 | Taibandal H.S. School, Shipahijala Tripura | PWD | 27 | 0 | 27 | 0 | 853 | 853 | 853 | Partly brownfield | 853 | SPA | 2014-15 | 300 | 0 | 300 | 496.09 | 300 | 300 | Work raised upto lintel level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | Taibandal H.S. School, Shipahijala Tripura | PWD | 27 | 0 | 27 | 0 |  |  |  | Partly brownfield | 300 | Niti Aayog | 2015-16 | 150 | 150 | 0 |  | 0 | 0 | Work raised upto lintel level. | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0
102 | Up gradation of infrastructure of Taibandal H.S School under Sepahijala District | PWD | 27 | 0 | 27 | 0 |  |  |  | Partly brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 |  | 180 | 180 | Work raised upto lintel level. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
103 | Kathalia H.S. School, Shipahijala Tripura | PWD | 29 | 29 | 0 | 0 | 553 | 553 | 553 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 0 |  | 500 | 0 | Structural work completed, finishing work is in progress. | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0
104 | Melaghar H.S. School, Shipahijala Tripura | PWD | 31 | 34 | 0 | -3 | 816 | 816 | 816 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 0 |  | 100 | 0 | Completed | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0
105 | Melaghar H.S. School, Shipahijala Tripura | PWD | 31 | 34 | 0 | -3 |  |  |  | brownfield | 300 | SPA | 2012-13 | 290 | 0 | 290 |  | 300 | 270 | Completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
106 | Melaghar H.S. School, Shipahijala Tripura | PWD | 31 | 34 | 0 | -3 |  |  |  | brownfield | 516 | Niti Aayog | 2015-16 | 129 | 129 | 0 |  | 316 | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0
107 | Sonamura Girls H.S. School, Shipahijala Tripura (Phase I) | PWD | 31 | 0 | 25 | 11 | 504 | 504 | 504 | brownfield | 504 | SPA | 2007-08 | 453.6 | 0 | 453.6 |  | 453.6 | 250 | Completed | 0 | 0 | 203.6 | 0 | 0 | 0 | 0 | 0
108 | Sonamura Girls H.S. School, Shipahijala Tripura (Phase II) | PWD | 36 | 0 | 25 | 11 | 50 | 50 | 50 | brownfield | 50 | SCA | 2012-13 | 50 | 0 | 50 | 170.53 | 0 | 0 | Structural work is in progress. | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
109 | Sonamura Girls H.S. School, Shipahijala Tripura(Phase III) | PWD | 36 | 0 | 25 | 11 | 252 | 252 | 126 | brownfield | 252 | SCA | 2014-15 | 126 | 0 | 126 |  | 126 | 126 | Structural work is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | Sonamura Girls H.S. School, Shipahijala Tripura | PWD | 36 | 0 | 25 | 11 | 100 | 100 | 100 | brownfield | 100 | SDS | 2015-16 | 100 | 100 | 0 |  | 0 | 0 | Structural work is in progress. | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0
111 | Bharat Sadar Para Class XII School, Khowai Tripura | PWD | 29 | 0 | 15 | 14 | 310 | 300 | 300 | brownfield | 300 | SDS | 2015-16 | 300 | 300 | 0 |  | 0 | 0 | Work order issued | 0 | 0 | 0 | 100 | 200 | 0 | 0 | 0
112 | Tulasikhar Rajnagar H.S. School, Khowai Tripura | PWD | 34 | 10 | 11 | 13 | 300 | 300 | 300 | brownfield | 300 | SDS | 2015-16 | 300 | 300 | 0 |  | 0 | 0 | Tender Called | 0 | 0 | 0 | 100 | 200 | 0 | 0 | 0
113 | Hrishyamuk H.S. School, South Tripura | PWD | 26 | 0 | 31 | -5 | 723 | 723 | 723 | brownfield | 150 | SPA | 2013-14 | 122.5 | 0 | 122.5 | 437.59 | 300 | 67.5 | Finishing work is in progress in front and west block. | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0
114 | Arjyacolony H.S. School, South Tripura | PWD | 31 | 20 | 5 | 6 | 655.38 | 655 | 655 | brownfield | 100 | SPA | 2012-13 | 100 | 0 | 100 | 360.03 | 100 | 62.5 | East & South block completed & handed over, work is in progress for northen block. | 0 | 0 | 37.5 | 0 | 0 | 0 | 0 | 0
115 | Arjyacolony H.S. School, South Tripura | PWD | 31 | 20 | 5 | 6 |  |  |  | brownfield | 455 | Niti Aayog | 2015-16 | 200 | 200 | 0 |  | 95 | 0 | East & South block completed & handed over, work is in progress for northen block. | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0
116 | Arjyacolony H.S. School, South Tripura | PWD | 31 | 20 | 5 | 6 |  |  |  | brownfield | 105 | SPA | 2013-14 | 105 | 0 | 105 |  | 105 | 0 | East & South block completed & handed over, work is in progress for northen block. | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 0
117 | Silachari H.S. School, Gomati Tripura | PWD | 32 | 0 | 30 | 2 | 972 | 972 | 90 | brownfield | 100 | SPA | 2013-14 | 95 | 0 | 95 | 508.97 | 90 | 90 | Work order issued. | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
118 | Karbook Panjihum H.S. School, Gomati Tripura | PWD | 43 | 6 | 26 | 11 | 787 | 787 | 90 | brownfield | 100 | SPA | 2013-14 | 95 | 0 | 95 | 463 | 90 | 90 | Demolishing work completed, structural drawing issued, foundation work will be started soon. | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0
119 | K.C. Girls H.S. School, Dhalai Tripura | PWD | 25 | 0 | 19 | 6 | 554 | 500 | 500 | brownfield | 500 | SPA | 2014-15 | 200 | 0 | 0 |  | 0 | 0 | Work order issued | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | K.K. Nagar H.S. School, Sepahijala Tripura | PWD | 22 | 9 | 18 | -5 | 793.04 | 793 | 200 | brownfield | 190 | SCA | 2012-13 | 190 | 0 | 0 | 372.54 | 290 | 0 | Out of four block, 1st block completed upto roof level, 2nd block upto lintel level, 3rd and 4th block foundation work is in progress. | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0
121 | Baikhora H.S. School, South Tripura | PWD | 33 | 6 | 22 | 5 | 609 | 609 | 609 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 33 | 435.22 | 33 | 33 | Work started | 67 | 67 | 0 | 0 | 0 | 0 | 0 | 0
122 | Baikhora H.S. School, South Tripura | PWD | 33 | 6 | 22 | 5 |  |  |  | brownfield | 36.67 | SPA | 2013-14 | 33 | 0 | 33 |  | 33 | 33 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | Boxanagar H.S. School, Sepahijala Tripura | PWD | 42 | 3 | 44 | -5 | 777 | 777 | 100 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 0 | 527.71 | 200 | 0 | Completed upto roof level except western side. | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0
124 | Mohanbogh High School, Sepahijala Tripura | PWD | 17 | 5 | 18 | -6 | 512.2 | 512.5 | 512.5 | brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 301.13 | 100 | 0 | Foundation work is in progress | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
125 | Mohanbogh High School, Sepahijala Tripura | PWD | 17 | 5 | 18 | -6 |  |  |  | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 0 |  | 160 | 0 | Foundation work is in progress | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0
126 | Umakanta Academy, West Tripura | PWD | 44 | 10 | 18 | 16 | 651.9 | 1600 | 1600 | Brownfield | 1600 | SPA | 2014-15 | 200 | 200 | 200 | 530.31 | 200 | 200 | Dismantling work completed and foundation work is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200
127 | Ramesh H.S. School, Gomati Tripura | PWD | 43 | 14 | 0 | 29 | 577 | 100 | 100 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 0 |  | 0 | 0 | Project cost 557 lac, amount sanctioned Rs.100.00 lacs, balance Rs.457.00 lac sanction required for calling tender. | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | Ganganagar High School, Dhalai | PWD | 26 | 6 | 0 | 20 | 350 | 350 | 350 | Brownfield | 350 | SDS | 2015-16 | 350 | 350 | 0 |  | 0 | 0 | DNIT under preperation by PWD | 0 | 0 | 0 | 100 | 250 | 0 | 0 | 0
129 | Rajnagar H.S. School, Belonia Tripura | PWD | 27 | 14 | 0 | 13 | 293 | 293 | 293 | Brownfield | 100 | SPA | 2012-13 | 100 | 0 | 100 | 424.66 | 100 | 82.5 | Phase-I completed by PWD. | 0 | 0 | 17.5 | 0 | 0 | 0 | 0 | 0
130 | Rajnagar H.S. School, Belonia Tripura | PWD | 27 | 14 | 0 | 13 |  |  |  | Brownfield | 55 | SPA | 2013-14 | 55 | 0 | 55 |  | 193 | 45 | Phase-I completed by PWD. | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
131 | Barpathari H.S. School, WestTripura | PWD | 35 | 0 | 32 | 3 | 600 | 600 | 300 | Brownfield | 600 | SDS | 2015-16 | 300 | 0 | 99.67 |  | 99.67 | 65 | Work order issued | 200.33 | 200.33 | 34.67 | 0 | 0 | 0 | 0 | 0
132 | Matabari H.S. School, Gomati Tripura | PWD | 28 | 27 | 0 | 1 | 436 | 400 | 400 | Brownfield | 400 | SPA | 2011-12 | 400 | 0 | 400 | 433.91 | 400 | 400 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | Teliamura H.S. School, Khowai Tripura | PWD | 38 | 4 | 0 | 34 | 600 | 600 | 300 | Brownfield | 600 | SDS | 2015-16 | 300 | 0 | 0 |  | 0 | 0 | Work order issued. Work to be started soon. | 300 | 150 | 0 | 0 | 0 | 0 | 0 | 0
134 | Belkhum Bari H.S. School, Unokoti Tripura | PWD | 23 | 0 | 0 | 23 | 575 | 575 | 575 | Brownfield | 100 | SPA | 2013-14 | 45 | 0 | 45 |  | 45 | 45 | DPR to be submitted by PWD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | Jampui H.S. School, North Tripura | PWD | 23 | 0 | 0 | 23 | 635 | 635 | 635 | Brownfield | 100 | SPA | 2013-14 | 45 | 0 | 45 |  | 45 | 45 | Work order issued. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | Gachiram Para High School, North Tripura | PWD | 16 | 4 | 0 | 12 | 916 | 916 | 916 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 |  | 90 | 90 | 1st,2nd,3rd call rejected. 4th call being invited. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | Laljuri H.S. School, North Tripura | PWD | 25 | 5 | 0 | 20 | 917 | 917 | 917 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 | 590.7 | 90 | 90 | Work order issued. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | Laljuri H.S. School, North Tripura | PWD | 25 | 5 | 0 | 20 |  |  |  | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 |  | 0 | 0 | Work order issued | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
139 | Raishyabari H.S. School, Dhalai Tripura | PWD | 30 | 0 | 30 | 0 | 500 | 500 | 500 | Brownfield | 100 | SPA | 2013-14 | 45 | 0 | 0 |  | 0 | 0 | Work order issued | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0
140 | Raishyabari H.S. School, Dhalai Tripura | PWD | 30 | 0 | 30 | 0 |  |  |  | Brownfield | 400 | Niti Aayog | 2015-16 | 100 | 100 | 0 |  | 0 | 0 | Work order issued | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
141 | Matai H.S. School, Belonia Tripura | PWD | 26 | 0 | 11 | 15 | 150 | 150 | 150 | Brownfield | 150 | SDS | 2015-16 | 150 | 0 | 150 | 117.12 | 0 | 34.673 | Work order issued. | 0 | 0 | 115.327 | 0 | 0 | 0 | 0 | 0
142 | Udaipur Girls H.S. School, Gomati Tripura | PWD | 35 | 37 | 0 | -2 | 500 | 500 | 500 | Brownfield | 500 | SPA | 2011-12 | 500 | 0 | 500 | 402.31 | 500 | 500 | Completed & ready for handing over. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | Sudhanya Debbarma Memorial Smriti H.S. School, Sepahijala Tripura | PWD | 30 | 25 | 0 | 5 | 500 | 500 | 500 | Brownfield | 500 | SPA | 2014-15 | 0 | 0 | 0 |  | 0 | 0 | Work order being issued | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | Upgradation of Dolugaon HS School North Tripura | PWD | 30 | 0 | 30 | 0 | 0 | 300 | 300 | Brownfield | 300 | SPA | 2014-15 | 0 | 0 | 0 | 0 | 0 | 0 | Drawing and concept paper under preperation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | Construction of DIET Kakraban | PWD | NA | NA | NA | NA | 200 | 200 | 200 | Greenfield | 200 | SPA | 2014-15 | 200 | 0 | 200 |  | 200 | 200 | Work completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | Maintenance of TBSE | PWD | NA | NA | NA | NA | 29.9 | 29.9 | 29.9 | Brownfield | 29.9 | SDS | 2015-16 | 29.9 | 0 | 29.9 |  | 29.9 | 0 | Completed | 0 | 0 | 29.9 | 0 | 0 | 0 | 0 | 0
147 | Santinagar HS | PWD | 19 | 9 | 10 | 0 | 200 | 0 | 0 | Brownfield | 200 | SDS | 2016-17 | 0 | 0 | 0 |  | 0 | 0 | Not yet started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | Kaulikura H. S. School at Kailashahar, Unakoti | PWD | NA | NA | NA | NA | 500 | 500 | 500 | Brownfield | 500 | SPA | 2011-12 | 500 | 50 | 250 | 415.09 | 500 | 250 | Completed | 200 | 200 | 0 | 0 | 0 | 50 | 0 | 0
149 | New Kunjaban Township H.S.School,Kunjaban,Agartala (phase I) | PWD | NA | NA | NA | NA | 620 | 620 | 620 | Brownfield | 620 | SPA | 2008-09 | 558 | 0 | 558 |  | 558 | 555 | Completed | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
150 | New Kunjaban Township School (Phase-II)/SH: Construction of boundary wall including gate, site development and internal road work with drainage system for new Kunjaban Township School at Agartala, West Tripura. | PWD | NA | NA | NA | NA | 200 | 200 | 200 | Brownfield | 200 | SPA | 2012-13 | 180 | 0 | 180 |  | 180 | 0 | Completed | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0
151 | Upgradation of Infrastructure of boundary wall, site development & internal road with dranage system of Shishu Bihar School, Agartala, West Tripura | PWD | NA | NA | NA | NA | 112.37 | 112.37 | 90 | Brownfield | 100 | SPA | 2013-14 | 88 | 10 | 78 |  | 78 | 50 | Completed | 0 | 0 | 28 | 0 | 0 | 10 | 0 | 0
152 | Upgradation of MTB Girls' H. S. School | PWD | NA | NA | NA | NA | 100 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 70 | 0 | 70 |  | 50 | 50 | Completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0
153 | Upgradation of MTB Girls' H. S. School (phase-I). | PWD | NA | NA | NA | NA | 250 | 250 | 250 | Brownfield | 250 | SPA | 2012-13 | 225 | 0 | 225 |  | 225 | 206.46 | Completed | 0 | 0 | 18.54 | 0 | 0 | 0 | 0 | 0
154 | Construction of 100 capacity Boys' Hostel for Daodarani Fazil H.S. Madrassa, Sonamura, Sepahijala District / Tilla Bazar Fazil H.S. Madrassa, Kailashahar, Unakoti / Bishalgarh Madrassa, Sepahijala District, Tripura | PWD | NA | NA | NA | NA | 1371 | 1371 | 1371 | Greenfield | 300 | SPA | 2012-13 | 300 | 0 | 300 |  | 995 | 270 | Work completed. Balance fund required. | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0
155 | 100 seated hostel at Tilabazar Madrassa | PWD | NA | NA | NA | NA |  |  |  | Greenfield | 55 | SPA | 2013-14 | 55 | 0 | 55 |  | 55 | 49.5 | Completed | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0
156 | 100 seated hostel at Bishalgarh Madrassa | PWD | NA | NA | NA | NA |  |  |  | Greenfield | 55 | SPA | 2013-14 | 55 | 0 | 55 |  | 55 | 49.5 | Completed | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0
157 | 100 seated hostel at Daodarani Fazil HS Madrassa | PWD | NA | NA | NA | NA |  |  |  | Greenfield | 55 | SPA | 2013-14 | 55 | 0 | 55 |  | 55 | 49.5 | Completed | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0
158 | 50 seated Hostel for Bishnupriya manipuri Boys, Rajbari HS Dharmanagar | PWD | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SPA | 2013-14 | 50 | 0 | 50 |  | 25 | 25 | Work stranded due to Court injunction | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0
159 | 50 seated Hostel for Bishnupriya manipuri Boys, Rajbari HS Dharmanagar | PWD | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SCA | 2012-13 | 50 | 0 | 50 |  | 25 | 25 | Work stranded due to Court injunction | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0
160 | Harachandra Class XII school | PWD | 29 | 4 | 25 | 0 | 0 | 100 | 100 | Greenfield | 100 | SCA | 2014-15 | 100 | 0 | 0 |  | 0 | 0 | Concept paper & drawing under preparation. | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | Renovation & upgradation of Kailashahar Govt Girls HS school | PWD | NA | NA | NA | NA | 472.08 | 472.08 | 357.23 | brownfield | 472.08 | NLCPR | 2010-11 | 357.23 | 0 | 357.23 |  | 357.23 | 357.23 | Work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | Construction of 50 Type III redsidential quarters for hostel superintendents | PWD | NA | NA | NA | NA | 821.84 | 210 | 210 | Greenfield | 210 | NEC | 2012-13 | 210 | 0 | 194 |  | 182 | 182 | Work on 13 hostels in progress out of which 9 already completed. | 16 | 16 | 12 | 0 | 0 | 0 | 0 | 0
163 | Nabinroy Bari High school Amarpur | PWD | 13 | 5 | 8 | 0 | 0 | 87.5 | 87.5 | brownfield | 87.5 | SDS | 2015-16 | 87.5 | 87.5 | 0 |  | 0 | 0 | Not yet started | 0 | 0 | 0 | 0 | 87.5 | 0 | 0 | 0
164 | Chandraipara HS School, Ambassa | PWD | 19 | 0 | 19 | 10 | 500 | 500 | 500 | brownfield | 500 | ACA | 2011-12 | 500 | 0 | 478.07 |  | 500 | 449.6 | Completed in Phase I | 21.93 | 21.93 | 28.47 | 0 | 0 | 0 | 0 | 0
165 | Manu HS, Sabroom | PWD | NA | NA | NA | NA | 400 | 400 | 400 | brownfield | 400 | SPA | 2009-10 | 360 | 180 | 180 |  | 400 | 0 | Completed | 180 | 180 | 180 | 0 | 0 | 0 | 180 | 180
166 | Radha Kishore Institution,(RKI) kailasahar, (Phase I) | PWD | NA | NA | NA | NA | 500 | 500 | 500 | brownfield | 500 | SPA | 2010-11 | 450 | 0 | 450 |  | 450 | 0 | Completed | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0
167 | Taibandal H.S. School, Shipahijala Tripura | SDM SNM | NA | NA | NA | NA | 2.5 | 2.5 | 2.5 | Greenfield | 2.5 | SCA | 2014-15 | 2.5 | 0 | 2.5 | NA | 2.5 | 2.5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | Vivekananda Vidya Mandir, Gomati Tripura | RD | 34 | 17 | 0 | 17 | 171 | 171 | 171 | Brownfield | 171 | SPA | 2013-14 | 171 | 0 | 76.95 | NA | 76.95 | 76.95 | Finishing work is in progress. | 94.05 | 94.05 | 0 | 0 | 0 | 0 | 0 | 0
169 | Asgar Rahamanpur High School, Sepahijala Tripura | RD | 14 | 0 | 9 | 5 |  | 100 | 100 | Greenfield | 100 | SDS | 2016-17 | 100 | 100 | 0 | NA | 0 | 0 | Drawing and Estimate under preparation by RD | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0
170 | Khumpui Academy H.S. School, North Tripura | TTAADC | 28 | 19 | 12 | -3 | 800 | 800 | 800 | Greenfield | 500 | SPA | 2012-13 | 500 | 50 | 450 |  | 450 | 450 | Work completed first phase. | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0
171 | Khumpui Academy H.S. School, North Tripura | TTAADC | 28 | 19 | 12 | -3 |  |  |  | Greenfield | 300 | SDS | 2015-16 | 300 | 300 | 0 |  | 0 | 0 | Work completed first phase. | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0
172 | St.John's High School (Private School), Killa, Udaipur ( boundary wall around the boys' & girls' hostels) | DM G | NA | NA | NA | NA | 30.2 | 30.2 | 30.2 | Brownfield | 30.2 | SCA | 2012-13 | 30.2 | 0 | 30.2 | NA | 30.2 | 0 | Completed | 0 | 0 | 30.2 | 0 | 0 | 0 | 0 | 0
173 | Upgradation of Darul Ullom Junior Madrasa, Rajdharnagar,Udaipur, Gomati | DM G | NA | NA | NA | NA | 15 | 15 | 15 | Brownfield | 15 | SCA | 2012-13 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
174 | Construction of 20 Nos. Madrassa building completed except Khedabari Islamia Junior Madrasa under Melaghar R.D.Block & Karaliamura Junior Madrasa | RD | NA | NA | NA | NA | 300 | 300 | 300 | Brownfield | 300 | SCA | 2012-13 | 300 | 0 | 300 | NA | 300 | 0 | Completed | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0
175 | Construction of 10(ten) Junior Basic (JB) School building under Chailengta Inspectorate of School, Dhalai, namely (i) Twaichandra Para (ii)Ramdhan C.P.(iii) Birchandra R.P (iv) Kunja Mohan R.P. (v) Budhijoy R.P.(vi) Ananda Hari R.P.(vii) Tankarai R.P. (viii) Nachya Kr. R.P. (ix) Madhya Chailengta (x) Badan C.P. | TTAADC | NA | NA | NA | NA | 135 | 135 | 135 | Brownfield | 126 | SCA | 2012-13 | 126 | 0 | 126 | NA | 126 | 0 | Completed | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0
176 | Construction of School building of Nishi Kumar Murasing Para Class XII School, South Tripura | DM South | NA | NA | NA | NA | 22 | 22 | 22 | Brownfield | 22 | SCA | 2013-14 | 22 | 0 | 22 |  | 22 | 22 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | Nishi Kumar Murasingh HS School Santirbazar | DM Gomati | NA | NA | NA | NA | 21.49 | 21.49 | 21.49 | Brownfield | 21.49 | SCA | 2013-14 | 10.75 | 0 | 10.75 |  | 10.75 | 10.75 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | Up-gradation of infrastructure of Nishi Kumar Murasingh Para High School, Santirbazar, South Tripura | DM Gomati | NA | NA | NA | NA | 110.06 | 110.06 | 110.06 | Brownfield | 110.06 | SPA | 2011-12 | 109.79 | 0 | 109.79 |  | 99.05 | 99.05 | Completed | 0 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0
179 | Construction of 120 metre boundary wall of Manaipathar High School | I/S, Sonamura | NA | NA | NA | NA | 19 | 19 | 19 | Greenfield | 8.4 | SCA | 2014-15 | 8.4 | 0 | 8.4 | NA | 8.4 | 8.4 | Work completed first phase. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 120 meterboundary wall of telkajla H.S | I/S, Sonamura | NA | NA | NA | NA | 17.5 | 17.5 | 17.5 | Greenfield | 17.5 | SCA | 2014-15 | 17.5 | 0 | 17.5 | NA | 17.5 | 17.5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | Construction of 4 nos. Rooms at telkajla HS School | RD | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SCA | 2014-15 | 50 | 0 | 50 | NA | 50 | 0 | Completed | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
182 | Construction of 100 HS and 150 High schools | RD | NA | NA | NA | NA | 487.84 | 487.84 | 487.84 | Greenfield | 487.84 | SDS | 2015-16 | 487.84 | 277.54 | 210.3 | NA | 179.7 | 0 | Work in progress | 0 | 0 | 210.3 | 0 | 0 | 277.54 | 0 | 0
183 | Procurement of furniture for Madrassa | DEE | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SDS | 2015-16 | 50 | 0 | 50 | NA | 0 | 0 | In progree. Supply order issued | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
184 | Development of site at East Harua for KV North tripura | RD | NA | NA | NA | NA | 24.647 | 24.647 | 24.647 | Greenfield | 24.647 | SDS | 2015-16 | 24.647 | 0.28 | 24.37 | NA | 0 | 0 | Work not yet taken up | 0 | 0 | 24.37 | 0 | 0.28 | 0 | 0 | 0
185 | Kalacherra Junior Madrasa under Kadamtala Block, North Tripura. | DM N | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
186 | Dakshin Padmabil Naydrone Junior Madrasa under Panisagar Block, North Tripura. | DM N | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
187 | Ratacherra Junior Madrasa under Kumarghat Block, Unakoti. | DM U | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
188 | South Samrupur Junior Madrasa under Gournagar Block, Unakoti. | DM U | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
189 | Naba Santi Ganj Pathalia Junior Madrasa under Bishalgarh, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
190 | Ghaniamara Junior Madrasa under Bishalgarh, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
191 | Bastali Naljala Junior Madrasa under Bishalgarh Sub-Division, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
192 | Telkajla Islamia Junior Madrasa under Melaghar RD Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
193 | Adampur Hasania Junior Madrasa under Boxanagar RD Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
194 | Khaddya Khala Islamia Junior Madrasa under Kathalia RD Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
195 | Rabigopalpara Islamia Junior Madrasa under Melaghar R.D.Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
196 | Karaliamura Junior Madrassa, Sonamura | DM SPJ | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
197 | Khedabari Islamia Junior Madrassa, Melaghar | DM SPJ | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0
198 | Renovation works at Padmapur HS for Kendriya Vidyalaya | DM North | NA | NA | NA | NA | 15.44 | 15.44 | 15.44 | Greenfield | 15.44 | SCA | 2014-15 | 15.44 | 0 | 15.44 | NA | 0 | 0 | Not started | 0 | 0 | 15.44 | 0 | 0 | 0 | 0 | 0
199 | Purchase of land for NCI sonamura | SDM Sonamura | NA | NA | NA | NA | 230 | 230 | 230 | Greenfield | 230 | SCA | 2014-15 | 230 | 0 | 230 | NA | 186.375 | 186.375 | Completed | 0 | 0 | 43.625 | 0 | 0 | 0 | 0 | 0
200 | Infrastructure development of R K Mission Viveknagar & Agartala | RK Mission | NA | NA | NA | NA | 442.9 | 249.11 | 249.11 | Greenfield | 442.9 | NLCPR | 2013-14 | 249.11 | 0 | 249.11 | NA | 249.11 | 249.11 | Work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | Upgradation of infrastructure of 100 HS | RD | NA | NA | NA | NA | 4541 | 4541 | 4541 | Greenfield | 4541 | NLCPR | 2006-07 | 4541 | 0 | 4439.7097 | NA | 4288 | 4288 | Work of 11 Schools in progress. Otherrs complete | 101.2903 | 10.47 | 151.7097 | 0 | 0 | 0 | 0 | 0
202 | Upgradation of infrastructure of 150 High schools | RD | NA | NA | NA | NA | 2811 | 2811 | 2811 | Greenfield | 2811 | NLCPR | 2006-07 | 2811 | 0 | 2811 | NA | 2695.22 | 2695.22 | Work of 7 Schools in progress. Otherrs complete | 0 | 0 | 115.78 | 0 | 0 | 0 | 0 | 0
203 | Ramkrishna Pathshala J.B. School, West Tripura. | Eng Cell | NA | NA | NA | NA | 30 | 30 | 30 | Greenfield | 30 | SCA | 2014-15 | 30 | 0 | 30 | 0 | 0 | 0 | Work to be started soon. | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0
204 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA | 793.04 | 793.04 | 793.04 | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | NA | 100 | 100 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA |  |  |  | Brownfield | 175.64 | SPA | 2013-14 | 79.04 | 0 | 79.04 | NA | 79.04 | 79.04 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA |  |  |  | Brownfield | 50 | SCA | 2012-13 | 50 | 0 | 25 | NA | 50 | 0 | Completed | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0
207 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA |  |  |  | Brownfield | 133 | SPA | 2013-14 | 106.5 | 0 | 40 | NA | 106.5 | 0 | Completed | 66.5 | 0 | 40 | 0 | 0 | 0 | 0 | 0
208 | Karaliamura Jr Madrassa, Sonamura | RD | NA | NA | NA | NA | 16.56 | 16.56 | 16.56 | Greenfield | 16.56 | SCA | 2013-14 | 16.56 | 0 | 8.28 | NA | 8.28 | 8.28 | Work raised above plinth level | 8.28 | 8.28 | 0 | 0 | 0 | 0 | 0 | 0
209 | Construction of new school building for Ishanchandranagar Pargana H. S. School at Bishalgarh, West Tripura | THCB | NA | NA | NA | NA | 406 | 406 | 406 | Brownfield | 406 | SPA | 2011-12 | 365.4 | 0 | 365.4 |  | 365.4 | 365.4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | Construction of Henry Derozio English Medium School, Kunjaban near basic Training College, Agartala, Tripura West. | THCB | NA | NA | NA | NA | 550 | 550 | 550 | Brownfield | 550 | SPA | 2011-12 | 495 | 0 | 495 |  | 495 | 495 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | Upgradation of infrastructure of Pragati Vidyabhawan H.S School at Agartala, West Tripura | THCB | NA | NA | NA | NA | 404 | 404 | 404 | Green field | 404 | SPA | 2011-12 | 404 | 0 | 404 |  | 404 | 363.6 | Completed | 0 | 0 | 40.4 | 0 | 0 | 0 | 0 | 0
212 | Upgradation of infrastructure of Tripurasundari H. S. School | PWD | NA | NA | NA | NA | 500 | 500 | 500 | Brownfield | 500 | SPA | 2011-12 | 500 | 0 | 500 |  | 500 | 500 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | Up-gradation of Infrastructure of Debendra Chowdhury Para S B School, Belcharra, Khowai. | TTAADC | NA | NA | NA | NA | 135 | 135 | 135 | Brownfield | 135 | SPA | 2012-13 | 135 | 13.5 | 121.5 |  | 135 | 121.5 | Completed | 0 | 0 | 0 | 0 | 0 | 13.5 | 0 | 0
214 | Construction of Kamalghat Higher Secondary School at Kamalghat (Phase- II). | THCB | NA | NA | NA | NA | 310 | 310 | 310 | Brownfield | 310 | SPA | 2012-13 | 279 | 0 | 279 |  | 279 | 279 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | Up gradation of infrastructure of Birendranagar Higher Secondary School Jirania under West District Tripura | THCB | NA | NA | NA | NA | 100 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 85 | 0 | 85 |  | 85 | 85 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | Construction of buildings for 33 numbers Scheme for Providing Quality Education in Madrassa @ Rs. 19.26 lakhs | RD | NA | NA | NA | NA | 635.58 | 635.58 | 635.58 | Brownfield | 635.58 | SPA | 2013-14 | 635.58 | 0 | 635.58 | NA | 635.58 | 635.58 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | Uniform grant to state government aided school | DSE | NA | NA | NA | NA | 55.22 | 55.22 | 55.22 | NA | 55.22 | SCA | 2013-14 | 55.22 | 21.25 | 33.97 | NA | 21.4 | 33.97 | Partially completed |  |  | 0 |  |  | 21.25 |  | 0
218 | Construction of DAT Amarpur HS School | PWD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | brownfield | 100 | SDS | 2016-17 | 100 | 100 | 0 |  | 0 | 0 | Not started | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0
[11 empty] | 54674.377 |  |  | 43991.647 | 6220.32 | 34976.6197 |  | 38302.847 | 28857.338 |  | 3369.7103 | 1883.26 | 6119.2817 | 950 | 1137.78 | 822.04 | 3310.5 | 575
6220.32
| Fund received during 2016-17 |  |  |  | Fund received |  |  | 43991.647 |  |  | Fund received during 2016-17 |  |  | 6220.32 |  | UC pending | 6119.2817
| SDS | 3090.32 |  |  | Drawn |  |  | 34976.6197 |  |  | Reallocated and drawn |  |  | 575
| SPA | 1024.25 |  |  | Balance |  |  | 9015.0273 |  |  | Reallocated but yet to be drawn |  |  | 2735.5 |  | DMs | 266.38
| SCS | 21.25 |  |  | Lapsed |  |  | 3369.7103 |  |  | Proposed for reallocation already |  |  | 950 |  | PWD | 2501.077
| Niti Aayog | 2084.5 |  |  | To be refunded |  |  | 1137.78 |  |  | To be reallocated |  |  | 822.04 |  | THCB | 2185.04
|  | 6220.32 |  |  | To be reallocated |  |  | 1772.04 |  |  | To be surrendered |  |  | 1137.78 |  | RD | 917.1597
[5 empty] | Reallocated but yet to be drawn |  |  | 2735.5 | [5 empty] | 6220.32 |  | TTAADC | 126
[8 empty] | 9015.0303 | [7 empty] | Others | 123.625
6119.2817
Note on B5: Author:

## THCB
Sl No. | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund received in 2016 | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status | Fund lapsed | Revalidation required | Pending UC | Reallocation proposed | Refund to be proposed | Reallocation to be done | Reallocated | Drawn | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Narsingarh H. S. School, Agartala, West Tripura | THCB | 37 | 0 | 20 | 17 | 750 | 800 | 800 | Brownfield | 150 | SPA | 2013-14 | 150 | 32.5 | 117.5 | 461.91 | 177.81 | 117.5 | Structural work completed in 1st floor | 0 | 0 | 0 | 0 | 0 | 32.5 | 0 | 0 | 0
2 | Lankamura H. S. School, Agartala, West Tripura | THCB | 28 | 4 | 12 | 12 | 1000 | 1000 | 100 | Brownfield | 100 | SCA untied | 2014-15 | 100 | 0 | 100 | 0 | 18.91 | 0 | Dismantling work is completed | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
3 | Bani Vidyapith Girls H. S. School, Agartala, West Tripura | THCB | 35 | 22 | 10 | 3 | 938.43 | 938 | 938 | Brownfield | 562.5 | SPA | 2008-09 | 562.5 | 0 | 562.5 | 780.16 | 562.5 | 562.5 | Major part of the building raised upto roof level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Bani Vidyapith Girls H. S. School, Agartala, West Tripura | THCB | 35 | 22 | 10 | 3 | 0 | 0 | 0 | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 0 | 180 | 180 | Major part of the building raised upto roof level. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
5 | Bani Vidyapith Girls H. S. School, Agartala, West Tripura | THCB | 35 | 22 | 10 | 3 | 0 | 0 | 0 | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 0 | 100 | 100 | Major part of the building raised upto roof level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 707.69 | 707.69 | 707.69 | Greenfield | 707.69 | SDS | 2015-16 | 707.69 | 0 | 0 | 232.34 | 0 | 0 | Finishing Work is in progress in the Eastern part and pilling work is in progress in the western part | 707.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 500 | 500 | 500 | Greenfield | 500 | SPA | 2010-11 | 500 | 0 | 500 | 417.2 | 600.48 | 500 | Finishing Work is in progress in the Eastern part and pilling work is in progress in the western part | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 46.44 | 46.44 | 46.44 | Greenfield | 46.44 | SDS | 2015-16 | 46.44 | 0 | 0 | 26 | 0 | 0 | Work in progress | 46.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Prachya Bharati H. S. School, Agartala, West Tripura | THCB | 31 | 26 | 15 | -10 | 50 | 50 | 50 | Greenfield | 50 | SPA | 2013-14 | 50 | 0 | 50 | 45 | 45 | 45 | Completed | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
10 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 | 815 | 65.11 | 65.11 | Brownfield | 65.11 | SDS | 2016-17 | 0 | 0 | 0 | 485.29 | 187.5 | 0 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 | 0 | 25 | 25 | Brownfield | 25 | SCA | 2013-14 | 12.5 | 0 | 12.5 | 0 | 12.5 | 12.5 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 | 0 | 100 | 100 | Brownfield | 100 | SCA | 2011-12 | 100 | 0 | 100 | 0 | 100 | 100 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Swami Dayalananda H. S. School, Agartala, West Tripura | THCB | 23 | 0 | 28 | -5 | 0 | 300 | 270 | Brownfield | 300 | SPA | 2012-13 | 300 | 30 | 270 | 0 | 270 | 270 | Finishing Work is in progress | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0
14 | Ramthakur Pathshala Girls H.S. School, Agartala, West Tripura | THCB | 27 | 28 | 0 | -1 | 717 | 250 | 250 | Brownfield | 250 | SPA | 2012-13 | 250 | 0 | 250 | 484.87 | 380.87 | 225 | Structural work Completed. | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
15 | Ramthakur Pathshala Girls H.S. School, Agartala, West Tripura | THCB | 27 | 28 | 0 | -1 | 0 | 280 | 280 | Brownfield | 280 | SPA | 2013-14 | 252 | 0 | 252 | 10.47 | 252 | 252 | Structural work Completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Ramthakur Pathshala Boys H.S. School, Agartala, West Tripura | THCB | 22 | 1 | 24 | -3 | 750 | 750 | 750 | Brownfield | 30 | SCA | 2013-14 | 15 | 0 | 15 | 478.9 | 52.53 | 15 | Finishing work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Ramthakur Pathshala Boys H.S. School, Agartala, West Tripura | THCB | 22 | 1 | 24 | -3 | 0 | 0 | 0 | Brownfield | 300 | SPA | 2012-13 | 300 | 0 | 300 | 0 | 300 | 270 | Finishing work is in progress | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0
18 | Ramthakur Pathshala Boys H.S. School, Agartala, West Tripura | THCB | 22 | 1 | 24 | -3 | 0 | 0 | 0 | Brownfield | 100 | SCA | 2011-12 | 100 | 0 | 100 | 0 | 100 | 100 | Finishing work is in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | Kamini Kumar Singha Memorial H.S. School, Agartala, West Tripura | THCB | 38 | 8 | 20 | 10 | 550 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 355.84 | 266.7 | 97.5 | Plastering work is going on. | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0
20 | Kabiraj Tilla H.S. School, Agartala, West Tripura | THCB | 26 | 0 | 32 | -6 | 1987 | 200 | 200 | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 457.38 | 0.482 | 0 | Column raised upto roof level in under ground floor. | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0
21 | Office Tilla H.S. School, Bishalgarh, West Tripura | THCB | 36 | 0 | 41 | -5 | 900 | 900 | 400 | Brownfield | 100 | SPA | 2013-14 | 85 | 0 | 85 | 452.59 | 85 | 85 | GF roof custing completed, Brickwork and plastering is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | Office Tilla H.S. School, Bishalgarh, West Tripura | THCB | 36 | 0 | 41 | -5 | 0 | 0 | 0 | Brownfield | 800 | Niti Aayog | 2015-16 | 300 | 300 | 0 | 0 | 214.65 | 0 | Work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
23 | Sakhicharan H.S. School, Agartala, West Tripura | THCB | 25 | 0 | 29 | -4 | 1529.97 | 100 | 100 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 476.31 | 30 | 30 | Temporary Structure Completed and dismentling work will be started after Durga Puja. | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0
24 | Bishalgarh Town Girls High School, Bishalgarh, West Tripura | THCB | 21 | 0 | 40 | -19 | 400 | 400 | 200 | Brownfield | 200 | SDS | 2015-16 | 200 | 200 | 0 | 314.71 | 0.72 | 0 | Dismantling Completed and clear site handover to THCB | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0
25 | Golaghati High School, Bishalgarh, West Tripura | THCB | 21 | 0 | 25 | -4 | 580.78 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 280.51 | 100 | 90 | Finishing work is in progress in 1st phase and work order issued for 2nd phase of the work | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
26 | Golaghati High School, Bishalgarh, West Tripura | THCB | 21 | 0 | 25 | -4 | 0 | 481 | 481 | Brownfield | 481 | Niti Ayog | 2015-16 | 240.5 | 240.5 | 0 | 0 | 108.38 | 0 | Finishing work is in progress in 1st phase and work order issued for 2nd phase of the work | 0 | 0 | 0 | 0 | 0 | 0 | 240.5 | 0 | 0
27 | Baidyar Dighi H.S. School, Bishalgarh, West Tripura | THCB | 30 | 4 | 21 | 5 | 700 | 700 | 100 | Brownfield | 100 | SPA | 2013-14 | 80 | 0 | 80 | 471.6 | 80 | 80 | Work raised upto P.L. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | Khowai Girls H.S. School, Khowai Tripura | THCB | 34 | 11 | 39 | -16 | 1000 | 1000 | 1000 | brownfield | 200 | SPA | 2013-14 | 90 | 0 | 90 | 478.49 | 90 | 90 | Structural work completed, brick wall and finishing work in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | Khowai Girls H.S. School, Khowai Tripura | THCB | 34 | 11 | 39 | -16 | 0 | 0 | 0 | brownfield | 800 | Niti Aayog | 2015-16 | 300 | 300 | 0 | 0 | 321.68 | 0 | Structural work completed, brick wall and finishing work in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0
30 | Pallimangal H.S. School, West Tripura | THCB | 35 | 12 | 17 | 6 | 958 | 958 | 958 | brownfield | 500 | SPA | 2010-11 | 450 | 0 | 450 | 420.83 | 450 | 450 | First phase of work is completed & handed over. In second phase, brick and finishing work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | Pallimangal H.S. School, West Tripura | THCB | 35 | 12 | 17 | 6 | 0 | 0 | 0 | brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 378.73 | 230.64 | 180 | First phase of work is completed & handed over. In second phase, brick and finishing work in progress | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
32 | Vidyasagar High School, West Tripura | THCB | 21 | 0 | 19 | 2 | 567.5 | 567.5 | 567.5 | brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 239.16 | 45 | 45 | 50% building reached upto plinth level. | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0
33 | Champaknagar H.S. School, West Tripura | THCB | 29 | 0 | 21 | 8 | 1405.93 | 1405 | 1405 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 450.715 | 0.18 | 0 | Work to be started soon. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
34 | Barjala Binapani H.S. School, West Tripura | THCB | 29 | 3 | 18 | 8 | 1311.18 | 1311 | 1311 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 464.64 | 100 | 100 | Raised upto plinth level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | Ranir Goan H.S. School, West Tripura | THCB | 31 | 10 | 20 | 1 | 1732.93 | 1732 | 1732 | brownfield | 155.4 | SCA | 2014-15 | 100 | 0 | 100 | 488.5 | 6.73 | 0 | Work order issued. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
36 | Sankaracharyya Vidyaniketan, West Tripura | THCB | 27 | 8 | 34 | -15 | 907 | 907 | 907 | brownfield | 462 | SPA | 2012-13 | 415.8 | 0 | 415.8 | 409.28 | 415.8 | 415.8 | 70% Structural work completed phase-I portion. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | Bokafa H.S. School, South Tripura | THCB | 33 | 8 | 28 | -3 | 700 | 700 | 700 | brownfield | 100 | SPA | 2013-14 | 100 | 50 | 50 | 458.58 | 64.86 | 0 | Pilling is in progress. | 0 | 0 | 50 | 0 | 0 | 50 | 0 | 0 | 0
38 | Uttar Maheshpur S.B. School, Sepahijala Tripura | THCB | 17 | 0 | 12 | 5 | 232 | 100 | 100 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 184.78 | 145 | 100 | 40% GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | Bhabanipur H.S. School, Sepahijala Tripura | THCB | 15 | 2 | 12 | 1 | 100 | 100 | 100 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 0 | 0 | 0 | Work is not required. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
40 | Nutan Nagar Girls H.S. School, Sepahijala Tripura | THCB | 26 | 26 | 0 | 0 | 750 | 750 | 750 | brownfield | 25 | SCA | 2013-14 | 12.5 | 0 | 12.5 | 366.48 | 12.5 | 12.5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | Nutan Nagar Girls H.S. School, Sepahijala Tripura | THCB | 26 | 26 | 0 | 0 | 0 | 0 | 0 | brownfield | 300 | SPA | 2012-13 | 290 | 0 | 290 | 0 | 270 | 270 | Completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
42 | Nutan Nagar Girls H.S. School, Sepahijala Tripura | THCB | 26 | 26 | 0 | 0 | 0 | 0 | 0 | brownfield | 100 | SCA | 2011-12 | 100 | 0 | 100 | 0 | 100 | 100 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | Bishramganj H.S. School, Sepahijala Tripura | THCB | 48 | 0 | 35 | 13 | 904 | 904 | 904 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 465.268 | 100 | 100 | GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | Bishramganj H.S. School, Sepahijala Tripura | THCB | 48 | 0 | 35 | 13 | 0 | 0 | 0 | brownfield | 200 | SPA | 2013-14 | 180 | 0 | 180 | 0 | 180 | 180 | GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | Bishramganj H.S. School, Sepahijala Tripura | THCB | 48 | 0 | 35 | 13 | 0 | 0 | 0 | brownfield | 439 | Niti Aayog | 2015-16 | 220 | 220 | 0 | 0 | 0 | 0 | GF roof casting has been completed. | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0
46 | Rajnagar H.S. School, West Tripura | THCB | 25 | 0 | 18 | 7 | 397 | 397 | 397 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 424.68 | 121.83 | 100 | Pile work is in progress. Out of 193, 145 nos pile work completed. Arrangement is being made for load test. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | Ramkrishna Ashram Vidyamandir High School, West Tripura | THCB | 29 | 0 | 22 | 7 | 794.72 | 520 | 520 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 293.57 | 13.34 | 0 | Dismantling work is going on. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
48 | Nidaya H.S. School, Sepahijala Tripura | THCB | 24 | 0 | 0 | 24 | 465 | 100 | 100 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 0 | 0 | 0 | 100 Lac sanctioned by P&C but project proposal of Rs.463.00 lacs send to P&C for getting sectioned. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
49 | Bodhjung Boys H.S. School, West Tripura | THCB | 35 | 0 | 22 | 13 | 1306 | 1306 | 1306 | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 447.8 | 392.89 | 180 | Structural work , B/W , plastering work in northen block is completed, 50% of foundaton work in westren block is completed. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
50 | Khowai English Medium H.S. School,Khowai Tripura | THCB | 25 | 0 | 19 | 6 | 1000 | 300 | 300 | Brownfield | 300 | SDS | 2015-16 | 300 | 0 | 300 | 315.44 | 100 | 100 | Foundation work is in progress | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0
51 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 350 | 350 | 350 | Brownfield | 350 | SPA | 2009-10 | 315 | 0 | 315 | 252.12 | 315 | 315 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 115 | 115 | 115 | Brownfield | 115 | SCA | 2011-12 | 115 | 0 | 115 | 115.02 | 115 | 115 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 200 | 200 | 200 | Brownfield | 200 | SPA | 2012-13 | 180 | 0 | 180 | 0 | 180 | 180 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 210 | 210 | 210 | Brownfield | 210 | SPA | 2013-14 | 189 | 0 | 189 | 0 | 189 | 189 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | Khudiram English Medium H.S. School, Tripura | THCB | 21 | 32 | 0 | -11 | 135.61 | 135.61 | 135.61 | Brownfield | 135.61 | SDS | 2015-16 | 135.61 | 0 | 135.61 | 0 | 0 | 0 | In progress | 0 | 0 | 135.61 | 0 | 0 | 0 | 0 | 0 | 0
56 | M.G.M. H.S. School, WestTripura | THCB | 32 | 16 | 15 | 1 | 1049 | 1049 | 1049 | Brownfield | 250 | SPA | 2012-13 | 250 | 25 | 225 | 317.48 | 250 | 225 | Work of FF is in finishing stage, work of the main building in old premicess reached above PL. | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
57 | M.G.M. H.S. School, WestTripura | THCB | 32 | 16 | 15 | 1 | 1049 | 0 | 0 | 0 | 500 | SPA | 2009-10 | 450 | 0 | 450 | 432.03 | 450 | 450 | Work of FF is in finishing stage, work of the main building in old premicess reached above PL. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | M.G.M. H.S. School, WestTripura | THCB | 32 | 16 | 15 | 1 | 1049 | 0 | 0 | Brownfield | 187.5 | SPA | 2013-14 | 187.5 | 18.75 | 168.75 | 0 | 168.75 | 168.75 | Work of FF is in finishing stage, work of the main building in old premicess reached above PL. | 0 | 0 | 0 | 0 | 0 | 18.75 | 0 | 0 | 0
59 | Chandrapur Colony H.S. School, WestTripura | THCB | 30 | 10 | 38 | -18 | 800 | 800 | 800 | Brownfield | 150 | SPA | 2013-14 | 150 | 32.5 | 117.5 | 447.135 | 147.5 | 117.5 | 50% Structural part has been completed. | 0 | 0 | 0 | 0 | 0 | 32.5 | 0 | 0 | 0
60 | Kumari Madhuti Rupasree High School, Khowai Tripura | THCB | 21 | 0 | 22 | -1 | 416.95 | 450 | 225 | Greenfield | 450 | SDS | 2015-16 | 225 | 225 | 0 | 277.92 | 63 | 0 | Structural work raised upto PL. | 0 | 0 | 0 | 0 | 0 | 0 | 225 | 0 | 0
61 | Bishalgarh Class XII School, WestTripura | THCB | 43 | 30 | 0 | 13 | 920 | 520 | 520 | Brownfield | 520 | SPA | 2010-11 | 520 | 0 | 520 | 0 | 520 | 520 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | Bishalgarh Class XII School, WestTripura | THCB | 43 | 30 | 0 | 13 | 0 | 400 | 200 | Brownfield | 400 | SDS | 2015-16 | 200 | 200 | 0 | 0 | 10.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0
63 | Ranir Bazar H.S. School, West Tripura | THCB | 39 | 59 | 0 | -20 | 600 | 600 | 100 | brownfield | 100 | SCA | 2013-14 | 100 | 0 | 100 | 499.94 | 419.95 | 100 | Completed and handed over. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | AD Nagar Eng.Med. H.S. School, West Tripura | THCB | 29 | 0 | 34 | -5 | 1064 | 1064 | 1064 | Greenfield | 100 | SPA | 2013-14 | 45 | 0 | 45 | 451.409 | 211.37 | 45 | Slab casting for FF roof in !st block completed upto expansion joint. Reinforcement binding for PB in north west block is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | Subhas Nagar H.S. School, West Tripura | THCB | 25 | 0 | 21 | 4 | 724 | 724 | 724 | Brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 392.97 | 0 | 0 | Work order issued, auction tender invited for dismantling old structure. | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
66 | Construction of Ramnagar Girls' High School. | THCB | NA | NA | NA | NA | 40 | 40 | 40 | Brownfield | 40 | SCA | 2012-13 | 40 | 0 | 40 | 40 | 40 | 40 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | Construction of Karaimura H. S. School. | THCB | NA | NA | NA | NA | 52 | 52 | 52 | Brownfield | 52 | SCA | 2012-13 | 52 | 0 | 52 | 52 | 52 | 0 | Completed | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0
68 | Construction of Sahid Bhagat Singh Hindi Medium School (Phase-I). | THCB | NA | NA | NA | NA | 350 | 350 | 350 | Brownfield | 350 | SPA | 2009-10 | 315 | 0 | 315 | 0 | 315 | 311.69 | Completed | 0 | 0 | 3.31 | 0 | 0 | 0 | 0 | 0 | 0
69 | Construction of Sahid Bhagat Singh Hindi Medium School (Phase-II). | THCB | NA | NA | NA | NA | 35 | 35 | 35 | Brownfield | 35 | SCA | 2012-13 | 35 | 0 | 35 | 35 | 35 | 0 | Completed | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0
70 | Construction of Nabagram H. S. School. | THCB | 0 | 0 | 0 | 0 | 772 | 772 | 772 | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 722 | 390.73 | 90 | Completed | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
71 | Upgradation of infrastructure of Kalyanpur HS School | THCB | 0 | 0 | 0 | 0 | 500 | 500 | 250 | Brownfield | 500 | SDS | 2015-16 | 250 | 250 | 0 | 0 | 1 | 0 | Work order issued | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0
72 | Ram Krishna Vivekananda Vidyalaya, Agartala | THCB | 0 | 0 | 0 | 0 | 724 | 724 | 724 | Brownfield | 100 | SDS | 2016-17 | 0 | 0 | 0 | 0 | 0 | 0 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | Dr. B.R Ambedkar High School, Agartala | THCB | 0 | 0 | 0 | 0 | 520 | 520 | 520 | Brownfield | 520 | SPA | 2008-09 | 468.5 | 0 | 468.5 | 437.42 | 325.38 | 325.38 | Completed | 0 | 0 | 143.12 | 0 | 0 | 0 | 0 | 0 | 0
74 | Dr. B.R Ambedkar High School, Agartala | THCB | 0 | 0 | 0 | 0 | 218 | 218 | 218 | Brownfield | 218 | SPA | 2012-13 | 218 | 0 | 218 | 0 | 119.9 | 119.9 | Completed | 0 | 0 | 98.1 | 0 | 0 | 0 | 0 | 0 | 0
75 | Auditorium at St Paul's HS School Agartala | THCB | NA | NA | NA | NA | 461 | 461 | 461 | Greenfield | 150 | SPA | 2012-13 | 135 | 0 | 135 | 307.72 | 0.27 | 0 | Work started | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0
76 | Auditorium at St Paul's HS School Agartala | THCB | NA | NA | NA | NA | 0 | 0 | 0 | Greenfield | 150 | SPA | 2013-14 | 75 | 0 | 75 | 0 | 0 | 0 | Work started | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0
77 | Bardowali HS School | THCB | 0 | 0 | 0 | 0 | 900 | 900 | 830 | Brownfield | 500 | SPA | 2009-10 | 450 | 0 | 450 | 0 | 600.62 | 450 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | Bardowali HS School | THCB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfield | 200 | SPA | 2012-13 | 200 | 20 | 180 | 0 | 180 | 180 | Completed | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0
79 | Bardowali HS School | THCB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 0 | 200 | 170 | In progress | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0
209 | Construction of new school building for Ishanchandranagar Pargana H. S. School at Bishalgarh, West Tripura | THCB | NA | NA | NA | NA | 406 | 406 | 406 | Brownfield | 406 | SPA | 2011-12 | 365.4 | 0 | 365.4 | 0 | 365.4 | 365.4 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | Construction of Henry Derozio English Medium School, Kunjaban near basic Training College, Agartala, Tripura West. | THCB | NA | NA | NA | NA | 550 | 550 | 550 | Brownfield | 550 | SPA | 2011-12 | 495 | 0 | 495 | 0 | 495 | 495 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | Upgradation of infrastructure of Pragati Vidyabhawan H.S School at Agartala, West Tripura | THCB | NA | NA | NA | NA | 404 | 404 | 404 | Green field | 404 | SPA | 2011-12 | 404 | 0 | 404 | 0 | 404 | 363.6 | Completed | 0 | 0 | 40.4 | 0 | 0 | 0 | 0 | 0 | 0
214 | Construction of Kamalghat Higher Secondary School at Kamalghat (Phase- II). | THCB | NA | NA | NA | NA | 310 | 310 | 310 | Brownfield | 310 | SPA | 2012-13 | 279 | 0 | 279 | 0 | 279 | 279 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | Up gradation of infrastructure of Birendranagar Higher Secondary School Jirania under West District Tripura | THCB | NA | NA | NA | NA | 100 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 85 | 0 | 85 | 0 | 85 | 85 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 42478.13 | 34810.35 | 31335.35 |  | 19582.25 |  |  | 16338.94 | 2144.25 | 13440.56 | 17298.187 | 14314.992 | 11255.52 |  | 754.13 | 0 | 2185.04 | 0 | 0 | 208.75 | 1935.5 | 0
Note on B5: Author:

## PWD
Sl No. | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund received in 2016 | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status | Fund lapsed | Revalidation required | Pending UC | Reallocation proposed | Refund to be proposed | Reallocation to be done | Reallocated | Drawn | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
80 | Kirit Bikram Institute(KBI),Udaipur (PhaseI) | PWD | NA | NA | NA | NA | 400 | 400 | 400 | Brownfield | 400 | SPA | 2009-10 | 360 | 0 | 360 | 0 | 360 | 235 | Completed and handed over. | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0
81 | Bijoy Kumar Girls H. S. School, Agartala, West Tripura | PWD | 33 | 8 | 23 | 2 | 874 | 874 | 680 | Brownfield | 200 | SPA | 2012-13 | 200 | 0 | 200 | 640.84 | 180 | 145 | GF work 70% completed, FF work 50% completed and foundation work of remaining part 75% completed | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0
82 | Bijoy Kumar Girls H. S. School, Agartala, West Tripura | PWD | 33 | 8 | 23 | 2 | 0 | 0 | 0 | Brownfield | 99 | SPA | 2013-14 | 85 | 0 | 85 | 0 | 65 | 65 | GF work 70% completed, FF work 50% completed and foundation work of remaining part 75% completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
83 | Bijoy Kumar Girls H. S. School, Agartala, West Tripura | PWD | 33 | 8 | 23 | 2 | 0 | 0 | 0 | Brownfield | 390 | Niti Aayog | 2015-16 | 195 | 195 | 195 | 0 | 195 | 195 | GF work 70% completed, FF work 50% completed and foundation work of remaining part 75% completed | 0 | 0 | 0 | 0 | 0 | 0 | 195 | 195 | 0
84 | Netaji Subhash Vidyaniketan, Agartala, West Tripura(Phase III) | PWD | 43 | 21 | 19 | 3 | 840 | 840 | 840 | Brownfield | 840 | SPA | 2014-15 | 500 | 300 | 200 | 538.92 | 200 | 200 | Dismantling Work complete. | 0 | 0 | 0 | 0 | 200 | 100 | 0 | 0 | 0
85 | Upgradation of infrastructure of NSV under ACA/Phase-II | PWD | 43 | 21 | 19 | 3 | 263.76 | 300 | 300 | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | 100 | 100 | 100 | Work Completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | Earth filling at the back side water bodies at NSV and Construction of boundary wall. | PWD | NA | NA | NA | NA | 50 | 25 | 25 | Brownfield | 25 | SCA | 2013-14 | 25 | 0 | 25 | 25 | 25 | 25 | Work Almost Completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | Upgradation of infrastructure of NSV etc. Dev. Playground with drainage facilities and installation of one befitting entrance gate at mid section, Construction of storm water drainage. | PWD | NA | NA | NA | NA | 233 | 233 | 233 | Brownfield | 233 | SDS | 2015-16 | 233 | 0 | 233 | 233 | 233 | 233 | 3nos. Work order issued. Earth work in field in progress. Other works not yet started. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | Upgradation of Infrastructure of boundary wall, site development & internal road with dranage system of Shishu Bihar School, Agartala, West Tripura | PWD | NA | NA | NA | NA | 100 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 90 | 12 | 78 | 0 | 78 | 50 | Completed | 0 | 0 | 28 | 0 | 0 | 12 | 0 | 0 | 0
89 | Baghan H.S. School, North Tripura | PWD | 25 | 10 | 33 | -18 | 500 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 | 0 | 90 | 90 | DNIT under preperation by PWD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | Baghan H.S. School, North Tripura | PWD | 25 | 10 | 33 | -18 | 0 | 0 | 0 | Brownfield | 400 | Niti Aayog | 2015-16 | 100 | 100 | 0 | 0 | 0 | 0 | DNIT under preperation by PWD | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0
91 | Dharmanagar Girls H.S. School, North Tripura | PWD | 25 | 28 | 0 | 11 | 450 | 450 | 450 | Brownfield | 213 | SPA | 2006-07 | 191.7 | 0 | 191.7 | 0 | 191.7 | 175 | Completed | 0 | 0 | 16.7 | 0 | 0 | 0 | 0 | 0 | 0
92 | Dharmanagar Girls H.S. School, North Tripura (PhaseII) | PWD | 39 | 28 | 0 | 11 | 0 | 0 | 0 | Brownfield | 450 | SPA | 2012-13 | 450 | 0 | 450 | 0 | 405 | 298.19 | Completed | 0 | 0 | 151.81 | 0 | 0 | 0 | 0 | 0 | 0
93 | Dharmanagar Boys H.S. School,(BBI)(Phase II) | PWD | 39 | 28 | 0 | 11 | 248 | 248 | 248 | Brownfield | 248 | SPA | 2007-08 | 223.2 | 0 | 223.2 | 0 | 223.2 | 188.64 | Completed | 0 | 0 | 34.56 | 0 | 0 | 0 | 0 | 0 | 0
94 | Kanchanpur H.S. School, North Tripura | PWD | 34 | 32 | 0 | 2 | 400 | 400 | 400 | Brownfield | 400 | SPA | 2008-09 | 360 | 0 | 59.8 | 0 | 360 | 59.8 | Completed | 300.2 | 300.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | Chawmanu H.S. School, Dhalai Tripura | PWD | 37 | 10 | 8 | 19 | 600 | 222.35 | 45 | Brownfield | 90 | SPA | 2013-14 | 45 | 0 | 45 | 0 | 0 | 0 | Work order issued, existing structure demolished,foundation work started | 0 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 0
96 | Chawmanu H.S. School, Dhalai Tripura | PWD | 37 | 10 | 8 | 19 | 0 | 500 | 150 | Brownfield | 500 | Niti Aayog | 2015-16 | 150 | 150 | 0 | 0 | 0 | 0 | Work order issued, existing structure demolished,foundation work started | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0
97 | Anandabazar H.S. School, North Tripura | PWD | 31 | 10 | 27 | -6 | 720 | 720 | 90 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 | 0 | 90 | 90 | Tender under scrutiny | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | Anandabazar H.S. School, North Tripura | PWD | 31 | 10 | 27 | -6 | 0 | 0 | 0 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 0 | 0 | 0 | Tender under scrutiny | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
99 | Srirampur Suryamani M. H.S. School, Unakoti Tripura | PWD | 32 | 6 | 16 | 10 | 438 | 300 | 300 | brownfield | 300 | SDS | 2015-16 | 300 | 300 | 0 | 262.25 | 0 | 0 | Work order issued. | 0 | 0 | 0 | 200 | 100 | 0 | 0 | 0 | 0
100 | Taibandal H.S. School, Shipahijala Tripura | PWD | 27 | 0 | 27 | 0 | 853 | 853 | 853 | Partly brownfield | 853 | SPA | 2014-15 | 300 | 0 | 300 | 496.09 | 300 | 300 | Work raised upto lintel level. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | Taibandal H.S. School, Shipahijala Tripura | PWD | 27 | 0 | 27 | 0 | 0 | 0 | 0 | Partly brownfield | 300 | Niti Aayog | 2015-16 | 150 | 150 | 0 | 0 | 0 | 0 | Work raised upto lintel level. | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0
102 | Up gradation of infrastructure of Taibandal H.S School under Sepahijala District | PWD | 27 | 0 | 27 | 0 | 0 | 0 | 0 | Partly brownfield | 200 | SPA | 2013-14 | 200 | 0 | 200 | 0 | 180 | 180 | Work raised upto lintel level. | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
103 | Kathalia H.S. School, Shipahijala Tripura | PWD | 29 | 29 | 0 | 0 | 553 | 553 | 553 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 0 | 0 | 500 | 0 | Structural work completed, finishing work is in progress. | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | Melaghar H.S. School, Shipahijala Tripura | PWD | 31 | 34 | 0 | -3 | 816 | 816 | 816 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 0 | 0 | 100 | 0 | Completed | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | Melaghar H.S. School, Shipahijala Tripura | PWD | 31 | 34 | 0 | -3 | 0 | 0 | 0 | brownfield | 300 | SPA | 2012-13 | 290 | 0 | 290 | 0 | 300 | 270 | Completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
106 | Melaghar H.S. School, Shipahijala Tripura | PWD | 31 | 34 | 0 | -3 | 0 | 0 | 0 | brownfield | 516 | Niti Aayog | 2015-16 | 129 | 129 | 0 | 0 | 316 | 0 | Completed | 0 | 0 | 0 | 0 | 0 | 129 | 0 | 0 | 0
107 | Sonamura Girls H.S. School, Shipahijala Tripura (Phase I) | PWD | 31 | 0 | 25 | 11 | 504 | 504 | 504 | brownfield | 504 | SPA | 2007-08 | 453.6 | 0 | 453.6 | 0 | 453.6 | 250 | Completed | 0 | 0 | 203.6 | 0 | 0 | 0 | 0 | 0 | 0
108 | Sonamura Girls H.S. School, Shipahijala Tripura (Phase II) | PWD | 36 | 0 | 25 | 11 | 50 | 50 | 50 | brownfield | 50 | SCA | 2012-13 | 50 | 0 | 50 | 170.53 | 0 | 0 | Structural work is in progress. | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0
109 | Sonamura Girls H.S. School, Shipahijala Tripura(Phase III) | PWD | 36 | 0 | 25 | 11 | 252 | 252 | 126 | brownfield | 252 | SCA | 2014-15 | 126 | 0 | 126 | 0 | 126 | 126 | Structural work is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | Sonamura Girls H.S. School, Shipahijala Tripura | PWD | 36 | 0 | 25 | 11 | 100 | 100 | 100 | brownfield | 100 | SDS | 2015-16 | 100 | 100 | 0 | 0 | 0 | 0 | Structural work is in progress. | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0
111 | Bharat Sadar Para Class XII School, Khowai Tripura | PWD | 29 | 0 | 15 | 14 | 310 | 300 | 300 | brownfield | 300 | SDS | 2015-16 | 300 | 300 | 0 | 0 | 0 | 0 | Work order issued | 0 | 0 | 0 | 100 | 200 | 0 | 0 | 0 | 0
112 | Tulasikhar Rajnagar H.S. School, Khowai Tripura | PWD | 34 | 10 | 11 | 13 | 300 | 300 | 300 | brownfield | 300 | SDS | 2015-16 | 300 | 300 | 0 | 0 | 0 | 0 | Tender Called | 0 | 0 | 0 | 100 | 200 | 0 | 0 | 0 | 0
113 | Hrishyamuk H.S. School, South Tripura | PWD | 26 | 0 | 31 | -5 | 723 | 723 | 723 | brownfield | 150 | SPA | 2013-14 | 122.5 | 0 | 122.5 | 437.59 | 300 | 67.5 | Finishing work is in progress in front and west block. | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 0
114 | Arjyacolony H.S. School, South Tripura | PWD | 31 | 20 | 5 | 6 | 655.38 | 655 | 655 | brownfield | 100 | SPA | 2012-13 | 100 | 0 | 100 | 360.03 | 100 | 62.5 | East & South block completed & handed over, work is in progress for northen block. | 0 | 0 | 37.5 | 0 | 0 | 0 | 0 | 0 | 0
115 | Arjyacolony H.S. School, South Tripura | PWD | 31 | 20 | 5 | 6 | 0 | 0 | 0 | brownfield | 455 | Niti Aayog | 2015-16 | 200 | 200 | 0 | 0 | 95 | 0 | East & South block completed & handed over, work is in progress for northen block. | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0
116 | Arjyacolony H.S. School, South Tripura | PWD | 31 | 20 | 5 | 6 | 0 | 0 | 0 | brownfield | 105 | SPA | 2013-14 | 105 | 0 | 105 | 0 | 105 | 0 | East & South block completed & handed over, work is in progress for northen block. | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0
117 | Silachari H.S. School, Gomati Tripura | PWD | 32 | 0 | 30 | 2 | 972 | 972 | 90 | brownfield | 100 | SPA | 2013-14 | 95 | 0 | 95 | 508.97 | 90 | 90 | Work order issued. | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
118 | Karbook Panjihum H.S. School, Gomati Tripura | PWD | 43 | 6 | 26 | 11 | 787 | 787 | 90 | brownfield | 100 | SPA | 2013-14 | 95 | 0 | 95 | 463 | 90 | 90 | Demolishing work completed, structural drawing issued, foundation work will be started soon. | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0
119 | K.C. Girls H.S. School, Dhalai Tripura | PWD | 25 | 0 | 19 | 6 | 554 | 500 | 500 | brownfield | 500 | SPA | 2014-15 | 200 | 0 | 0 | 0 | 0 | 0 | Work order issued | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | K.K. Nagar H.S. School, Sepahijala Tripura | PWD | 22 | 9 | 18 | -5 | 793.04 | 793 | 200 | brownfield | 190 | SCA | 2012-13 | 190 | 0 | 0 | 372.54 | 290 | 0 | Out of four block, 1st block completed upto roof level, 2nd block upto lintel level, 3rd and 4th block foundation work is in progress. | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | Baikhora H.S. School, South Tripura | PWD | 33 | 6 | 22 | 5 | 609 | 609 | 609 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 33 | 435.22 | 33 | 33 | Work started | 67 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | Baikhora H.S. School, South Tripura | PWD | 33 | 6 | 22 | 5 | 0 | 0 | 0 | brownfield | 36.67 | SPA | 2013-14 | 33 | 0 | 33 | 0 | 33 | 33 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | Boxanagar H.S. School, Sepahijala Tripura | PWD | 42 | 3 | 44 | -5 | 777 | 777 | 100 | brownfield | 100 | SCA | 2012-13 | 100 | 0 | 0 | 527.71 | 200 | 0 | Completed upto roof level except western side. | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | Mohanbogh High School, Sepahijala Tripura | PWD | 17 | 5 | 18 | -6 | 512.2 | 512.5 | 512.5 | brownfield | 100 | SPA | 2013-14 | 100 | 0 | 100 | 301.13 | 100 | 0 | Foundation work is in progress | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
125 | Mohanbogh High School, Sepahijala Tripura | PWD | 17 | 5 | 18 | -6 | 0 | 0 | 0 | brownfield | 100 | SCA | 2014-15 | 100 | 0 | 0 | 0 | 160 | 0 | Foundation work is in progress | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | Umakanta Academy, West Tripura | PWD | 44 | 10 | 18 | 16 | 651.9 | 1600 | 1600 | Brownfield | 1600 | SPA | 2014-15 | 200 | 200 | 200 | 530.31 | 200 | 200 | Dismantling work completed and foundation work is in progress. | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 0
127 | Ramesh H.S. School, Gomati Tripura | PWD | 43 | 14 | 0 | 29 | 577 | 100 | 100 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 0 | 0 | 0 | 0 | Project cost 557 lac, amount sanctioned Rs.100.00 lacs, balance Rs.457.00 lac sanction required for calling tender. | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | Ganganagar High School, Dhalai | PWD | 26 | 6 | 0 | 20 | 350 | 350 | 350 | Brownfield | 350 | SDS | 2015-16 | 350 | 350 | 0 | 0 | 0 | 0 | DNIT under preperation by PWD | 0 | 0 | 0 | 100 | 250 | 0 | 0 | 0 | 0
129 | Rajnagar H.S. School, Belonia Tripura | PWD | 27 | 14 | 0 | 13 | 293 | 293 | 293 | Brownfield | 100 | SPA | 2012-13 | 100 | 0 | 100 | 424.66 | 100 | 82.5 | Phase-I completed by PWD. | 0 | 0 | 17.5 | 0 | 0 | 0 | 0 | 0 | 0
130 | Rajnagar H.S. School, Belonia Tripura | PWD | 27 | 14 | 0 | 13 | 0 | 0 | 0 | Brownfield | 55 | SPA | 2013-14 | 55 | 0 | 55 | 0 | 193 | 45 | Phase-I completed by PWD. | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0
131 | Barpathari H.S. School, WestTripura | PWD | 35 | 0 | 32 | 3 | 600 | 600 | 300 | Brownfield | 600 | SDS | 2015-16 | 300 | 0 | 99.67 | 0 | 99.67 | 65 | Work order issued | 200.33 | 200.33 | 34.67 | 0 | 0 | 0 | 0 | 0 | 0
132 | Matabari H.S. School, Gomati Tripura | PWD | 28 | 27 | 0 | 1 | 436 | 400 | 400 | Brownfield | 400 | SPA | 2011-12 | 400 | 0 | 400 | 433.91 | 400 | 400 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | Teliamura H.S. School, Khowai Tripura | PWD | 38 | 4 | 0 | 34 | 600 | 600 | 300 | Brownfield | 600 | SDS | 2015-16 | 300 | 0 | 0 | 0 | 0 | 0 | Work order issued. Work to be started soon. | 300 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | Belkhum Bari H.S. School, Unokoti Tripura | PWD | 23 | 0 | 0 | 23 | 575 | 575 | 575 | Brownfield | 100 | SPA | 2013-14 | 45 | 0 | 45 | 0 | 45 | 45 | DPR to be submitted by PWD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | Jampui H.S. School, North Tripura | PWD | 23 | 0 | 0 | 23 | 635 | 635 | 635 | Brownfield | 100 | SPA | 2013-14 | 45 | 0 | 45 | 0 | 45 | 45 | Work order issued. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | Gachiram Para High School, North Tripura | PWD | 16 | 4 | 0 | 12 | 916 | 916 | 916 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 | 0 | 90 | 90 | 1st,2nd,3rd call rejected. 4th call being invited. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | Laljuri H.S. School, North Tripura | PWD | 25 | 5 | 0 | 20 | 917 | 917 | 917 | Brownfield | 100 | SPA | 2013-14 | 90 | 0 | 90 | 590.7 | 90 | 90 | Work order issued. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | Laljuri H.S. School, North Tripura | PWD | 25 | 5 | 0 | 20 | 0 | 0 | 0 | Brownfield | 100 | SCA | 2014-15 | 100 | 0 | 100 | 0 | 0 | 0 | Work order issued | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0
139 | Raishyabari H.S. School, Dhalai Tripura | PWD | 30 | 0 | 30 | 0 | 500 | 500 | 500 | Brownfield | 100 | SPA | 2013-14 | 45 | 0 | 0 | 0 | 0 | 0 | Work order issued | 45 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | Raishyabari H.S. School, Dhalai Tripura | PWD | 30 | 0 | 30 | 0 | 0 | 0 | 0 | Brownfield | 400 | Niti Aayog | 2015-16 | 100 | 100 | 0 | 0 | 0 | 0 | Work order issued | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0
141 | Matai H.S. School, Belonia Tripura | PWD | 26 | 0 | 11 | 15 | 150 | 150 | 150 | Brownfield | 150 | SDS | 2015-16 | 150 | 0 | 150 | 117.12 | 0 | 34.673 | Work order issued. | 0 | 0 | 115.327 | 0 | 0 | 0 | 0 | 0 | 0
142 | Udaipur Girls H.S. School, Gomati Tripura | PWD | 35 | 37 | 0 | -2 | 500 | 500 | 500 | Brownfield | 500 | SPA | 2011-12 | 500 | 0 | 500 | 402.31 | 500 | 500 | Completed & ready for handing over. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | Sudhanya Debbarma Memorial Smriti H.S. School, Sepahijala Tripura | PWD | 30 | 25 | 0 | 5 | 500 | 500 | 500 | Brownfield | 500 | SPA | 2014-15 | 0 | 0 | 0 | 0 | 0 | 0 | Work order being issued | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | Upgradation of Dolugaon HS School North Tripura | PWD | 30 | 0 | 30 | 0 | 0 | 300 | 300 | Brownfield | 300 | SPA | 2014-15 | 0 | 0 | 0 | 0 | 0 | 0 | Drawing and concept paper under preperation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | Construction of DIET Kakraban | PWD | NA | NA | NA | NA | 200 | 200 | 200 | Greenfield | 200 | SPA | 2014-15 | 200 | 0 | 200 | 0 | 200 | 200 | Work completed. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | Maintenance of TBSE | PWD | NA | NA | NA | NA | 29.9 | 29.9 | 29.9 | Brownfield | 29.9 | SDS | 2015-16 | 29.9 | 0 | 29.9 | 0 | 29.9 | 0 | Completed | 0 | 0 | 29.9 | 0 | 0 | 0 | 0 | 0 | 0
147 | Santinagar HS | PWD | 19 | 9 | 10 | 0 | 200 | 0 | 0 | Brownfield | 200 | SDS | 2016-17 | 0 | 0 | 0 | 0 | 0 | 0 | Not yet started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | Kaulikura H. S. School at Kailashahar, Unakoti | PWD | NA | NA | NA | NA | 500 | 500 | 500 | Brownfield | 500 | SPA | 2011-12 | 500 | 50 | 250 | 415.09 | 500 | 250 | Completed | 200 | 200 | 0 | 0 | 0 | 50 | 0 | 0 | 0
149 | New Kunjaban Township H.S.School,Kunjaban,Agartala (phase I) | PWD | NA | NA | NA | NA | 620 | 620 | 620 | Brownfield | 620 | SPA | 2008-09 | 558 | 0 | 558 | 0 | 558 | 555 | Completed | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0
150 | New Kunjaban Township School (Phase-II)/SH: Construction of boundary wall including gate, site development and internal road work with drainage system for new Kunjaban Township School at Agartala, West Tripura. | PWD | NA | NA | NA | NA | 200 | 200 | 200 | Brownfield | 200 | SPA | 2012-13 | 180 | 0 | 180 | 0 | 180 | 0 | Completed | 0 | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0
151 | Upgradation of Infrastructure of boundary wall, site development & internal road with dranage system of Shishu Bihar School, Agartala, West Tripura | PWD | NA | NA | NA | NA | 112.37 | 112.37 | 90 | Brownfield | 100 | SPA | 2013-14 | 88 | 10 | 78 | 0 | 78 | 50 | Completed | 0 | 0 | 28 | 0 | 0 | 10 | 0 | 0 | 0
152 | Upgradation of MTB Girls' H. S. School | PWD | NA | NA | NA | NA | 100 | 100 | 100 | Brownfield | 100 | SPA | 2013-14 | 70 | 0 | 70 | 0 | 50 | 50 | Completed | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0
153 | Upgradation of MTB Girls' H. S. School (phase-I). | PWD | NA | NA | NA | NA | 250 | 250 | 250 | Brownfield | 250 | SPA | 2012-13 | 225 | 0 | 225 | 0 | 225 | 206.46 | Completed | 0 | 0 | 18.54 | 0 | 0 | 0 | 0 | 0 | 0
154 | Construction of 100 capacity Boys' Hostel for Daodarani Fazil H.S. Madrassa, Sonamura, Sepahijala District / Tilla Bazar Fazil H.S. Madrassa, Kailashahar, Unakoti / Bishalgarh Madrassa, Sepahijala District, Tripura | PWD | NA | NA | NA | NA | 1371 | 1371 | 1371 | Greenfield | 300 | SPA | 2012-13 | 300 | 0 | 300 | 0 | 995 | 270 | Work completed. Balance fund required. | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0
155 | 100 seated hostel at Tilabazar Madrassa | PWD | NA | NA | NA | NA | 0 | 0 | 0 | Greenfield | 55 | SPA | 2013-14 | 55 | 0 | 55 | 0 | 55 | 49.5 | Completed | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0
156 | 100 seated hostel at Bishalgarh Madrassa | PWD | NA | NA | NA | NA | 0 | 0 | 0 | Greenfield | 55 | SPA | 2013-14 | 55 | 0 | 55 | 0 | 55 | 49.5 | Completed | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0
157 | 100 seated hostel at Daodarani Fazil HS Madrassa | PWD | NA | NA | NA | NA | 0 | 0 | 0 | Greenfield | 55 | SPA | 2013-14 | 55 | 0 | 55 | 0 | 55 | 49.5 | Completed | 0 | 0 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0
158 | 50 seated Hostel for Bishnupriya manipuri Boys, Rajbari HS Dharmanagar | PWD | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SPA | 2013-14 | 50 | 0 | 50 | 0 | 25 | 25 | Work stranded due to Court injunction | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
159 | 50 seated Hostel for Bishnupriya manipuri Boys, Rajbari HS Dharmanagar | PWD | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SCA | 2012-13 | 50 | 0 | 50 | 0 | 25 | 25 | Work stranded due to Court injunction | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
160 | Harachandra Class XII school | PWD | 29 | 4 | 25 | 0 | 0 | 100 | 100 | Greenfield | 100 | SCA | 2014-15 | 100 | 0 | 0 | 0 | 0 | 0 | Concept paper & drawing under preparation. | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | Renovation & upgradation of Kailashahar Govt Girls HS school | PWD | NA | NA | NA | NA | 472.08 | 472.08 | 357.23 | brownfield | 472.08 | NLCPR | 2010-11 | 357.23 | 0 | 357.23 | 0 | 357.23 | 357.23 | Work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | Construction of 50 Type III redsidential quarters for hostel superintendents | PWD | NA | NA | NA | NA | 821.84 | 210 | 210 | Greenfield | 210 | NEC | 2012-13 | 210 | 0 | 194 | 0 | 182 | 182 | Work on 13 hostels in progress out of which 9 already completed. | 16 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0
163 | Nabinroy Bari High school Amarpur | PWD | 13 | 5 | 8 | 0 | 0 | 87.5 | 87.5 | brownfield | 87.5 | SDS | 2015-16 | 87.5 | 87.5 | 0 | 0 | 0 | 0 | Not yet started | 0 | 0 | 0 | 0 | 87.5 | 0 | 0 | 0 | 0
164 | Chandraipara HS School, Ambassa | PWD | 19 | 0 | 19 | 10 | 500 | 500 | 500 | brownfield | 500 | ACA | 2011-12 | 500 | 0 | 478.07 | 0 | 500 | 449.6 | Completed in Phase I | 21.93 | 21.93 | 28.47 | 0 | 0 | 0 | 0 | 0 | 0
165 | Manu HS, Sabroom | PWD | NA | NA | NA | NA | 400 | 400 | 400 | brownfield | 400 | SPA | 2009-10 | 360 | 180 | 180 | 0 | 400 | 0 | Completed | 180 | 180 | 180 | 0 | 0 | 0 | 180 | 180 | 0
166 | Radha Kishore Institution,(RKI) kailasahar, (Phase I) | PWD | NA | NA | NA | NA | 500 | 500 | 500 | brownfield | 500 | SPA | 2010-11 | 450 | 0 | 450 | 0 | 450 | 0 | Completed | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0
212 | Upgradation of infrastructure of Tripurasundari H. S. School | PWD | NA | NA | NA | NA | 500 | 500 | 500 | Brownfield | 500 | SPA | 2011-12 | 500 | 0 | 500 | 0 | 500 | 500 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | Construction of DAT Amarpur HS School | PWD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | brownfield | 100 | SDS | 2016-17 | 100 | 100 | 0 | 0 | 0 | 0 | Not started | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0
[7 empty] | 31315.47 | 30957.7 | 25894.13 |  | 23189.15 |  |  | 16077.63 | 3313.5 | 11018.67 | 8786.92 | 13850.3 | 8517.593 |  | 2320.46 | 1770.46 | 2501.077 | 600 | 1137.5 | 301 | 1275 | 575

## RD
Sl No. | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund received in 2016 | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status | Fund lapsed | Revalidation required | Pending UC | Reallocation proposed | Refund to be proposed | Reallocation to be done | Reallocated | Drawn | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
168 | Vivekananda Vidya Mandir, Gomati Tripura | RD | 34 | 17 | 0 | 17 | 171 | 171 | 171 | Brownfield | 171 | SPA | 2013-14 | 171 | 0 | 76.95 | NA | 76.95 | 76.95 | Finishing work is in progress. | 94.05 | 94.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | Asgar Rahamanpur High School, Sepahijala Tripura | RD | 14 | 0 | 9 | 5 | 0 | 100 | 100 | Greenfield | 100 | SDS | 2016-17 | 100 | 100 | 0 | NA | 0 | 0 | Drawing and Estimate under preparation by RD | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0
174 | Construction of 20 Nos. Madrassa building completed except Khedabari Islamia Junior Madrasa under Melaghar R.D.Block & Karaliamura Junior Madrasa | RD | NA | NA | NA | NA | 300 | 300 | 300 | Brownfield | 300 | SCA | 2012-13 | 300 | 0 | 300 | NA | 300 | 0 | Completed | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0
181 | Construction of 4 nos. Rooms at telkajla HS School | RD | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SCA | 2014-15 | 50 | 0 | 50 | NA | 50 | 0 | Completed | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0
182 | Construction of 100 HS and 150 High schools | RD | NA | NA | NA | NA | 487.84 | 487.84 | 487.84 | Greenfield | 487.84 | SDS | 2015-16 | 487.84 | 277.54 | 210.3 | NA | 179.7 | 0 | Work in progress | 0 | 0 | 210.3 | 0 | 0 | 277.54 | 0 | 0 | 0
184 | Development of site at East Harua for KV North tripura | RD | NA | NA | NA | NA | 24.647 | 24.647 | 24.647 | Greenfield | 24.647 | SDS | 2015-16 | 24.647 | 0.28 | 24.37 | NA | 0 | 0 | Work not yet taken up | 0 | 0 | 24.37 | 0 | 0.28 | 0 | 0 | 0 | 0
201 | Upgradation of infrastructure of 100 HS | RD | NA | NA | NA | NA | 4541 | 4541 | 4541 | Greenfield | 4541 | NLCPR | 2006-07 | 4541 | 0 | 4439.7097 | NA | 4288 | 4288 | Work of 11 Schools in progress. Otherrs complete | 101.2903 | 10.47 | 151.7097 | 0 | 0 | 0 | 0 | 0 | 0
202 | Upgradation of infrastructure of 150 High schools | RD | NA | NA | NA | NA | 2811 | 2811 | 2811 | Greenfield | 2811 | NLCPR | 2006-07 | 2811 | 0 | 2811 | NA | 2695.22 | 2695.22 | Work of 7 Schools in progress. Otherrs complete | 0 | 0 | 115.78 | 0 | 0 | 0 | 0 | 0 | 0
204 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA | 793.04 | 793.04 | 793.04 | Brownfield | 100 | SCA | 2012-13 | 100 | 0 | 100 | NA | 100 | 100 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA | 0 | 0 | 0 | Brownfield | 175.64 | SPA | 2013-14 | 79.04 | 0 | 79.04 | NA | 79.04 | 79.04 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA | 0 | 0 | 0 | Brownfield | 50 | SCA | 2012-13 | 50 | 0 | 25 | NA | 50 | 0 | Completed | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0
207 | Construction of 100 capacity Boys' Hostel at Baspukur Sr. Madrassa, Kathalia Block | RD | NA | NA | NA | NA | 0 | 0 | 0 | Brownfield | 133 | SPA | 2013-14 | 106.5 | 0 | 40 | NA | 106.5 | 0 | Completed | 66.5 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0
208 | Karaliamura Jr Madrassa, Sonamura | RD | NA | NA | NA | NA | 16.56 | 16.56 | 16.56 | Greenfield | 16.56 | SCA | 2013-14 | 16.56 | 0 | 8.28 | NA | 8.28 | 8.28 | Work raised above plinth level | 8.28 | 8.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | Construction of buildings for 33 numbers Scheme for Providing Quality Education in Madrassa @ Rs. 19.26 lakhs | RD | NA | NA | NA | NA | 635.58 | 635.58 | 635.58 | Brownfield | 635.58 | SPA | 2013-14 | 635.58 | 0 | 635.58 | NA | 635.58 | 635.58 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 9830.667 | 9930.667 | 9930.667 |  | 9596.267 |  |  | 9473.167 | 377.82 | 8800.2297 | 0 | 8569.27 | 7883.07 |  | 295.1203 | 112.8 | 917.1597 | 0 | 0.28 | 277.54 | 100 | 0

## TTAADC
Sl No. | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund received in 2016 | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status | Fund lapsed | Revalidation required | Pending UC | Reallocation proposed | Refund to be proposed | Reallocation to be done | Reallocated | Drawn | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
170 | Khumpui Academy H.S. School, North Tripura | TTAADC | 28 | 19 | 12 | -3 | 800 | 800 | 800 | Greenfield | 500 | SPA | 2012-13 | 500 | 50 | 450 | 0 | 450 | 450 | Work completed first phase. | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0
171 | Khumpui Academy H.S. School, North Tripura | TTAADC | 28 | 19 | 12 | -3 | 0 | 0 | 0 | Greenfield | 300 | SDS | 2015-16 | 300 | 300 | 0 | 0 | 0 | 0 | Work completed first phase. | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0
175 | Construction of 10(ten) Junior Basic (JB) School building under Chailengta Inspectorate of School, Dhalai, namely (i) Twaichandra Para (ii)Ramdhan C.P.(iii) Birchandra R.P (iv) Kunja Mohan R.P. (v) Budhijoy R.P.(vi) Ananda Hari R.P.(vii) Tankarai R.P. (viii) Nachya Kr. R.P. (ix) Madhya Chailengta (x) Badan C.P. | TTAADC | NA | NA | NA | NA | 135 | 135 | 135 | Brownfield | 126 | SCA | 2012-13 | 126 | 0 | 126 | NA | 126 | 0 | Completed | 0 | 0 | 126 | 0 | 0 | 0 | 0 | 0 | 0
213 | Up-gradation of Infrastructure of Debendra Chowdhury Para S B School, Belcharra, Khowai. | TTAADC | NA | NA | NA | NA | 135 | 135 | 135 | Brownfield | 135 | SPA | 2012-13 | 135 | 13.5 | 121.5 | 0 | 135 | 121.5 | Completed | 0 | 0 | 0 | 0 | 0 | 13.5 | 0 | 0 | 0
[7 empty] | 1070 | 1070 | 1070 |  | 1061 |  |  | 1061 | 363.5 | 697.5 | 0 | 711 | 571.5 |  | 0 | 0 | 126 | 350 | 0 | 13.5 | 0 | 0

## DM
Sl No. | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund received in 2016 | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status | Fund lapsed | Revalidation required | Pending UC | Reallocation proposed | Refund to be proposed | Reallocation to be done | Reallocated | Drawn | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
172 | St.John's High School (Private School), Killa, Udaipur ( boundary wall around the boys' & girls' hostels) | DM G | NA | NA | NA | NA | 30.2 | 30.2 | 30.2 | Brownfield | 30.2 | SCA | 2012-13 | 30.2 | 0 | 30.2 | NA | 30.2 | 0 | Completed | 0 | 0 | 30.2 | 0 | 0 | 0 | 0 | 0 | 0
173 | Upgradation of Darul Ullom Junior Madrasa, Rajdharnagar,Udaipur, Gomati | DM G | NA | NA | NA | NA | 15 | 15 | 15 | Brownfield | 15 | SCA | 2012-13 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
176 | Construction of School building of Nishi Kumar Murasing Para Class XII School, South Tripura | DM South | NA | NA | NA | NA | 22 | 22 | 22 | Brownfield | 22 | SCA | 2013-14 | 22 | 0 | 22 | 0 | 22 | 22 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | Nishi Kumar Murasingh HS School Santirbazar | DM Gomati | NA | NA | NA | NA | 21.49 | 21.49 | 21.49 | Brownfield | 21.49 | SCA | 2013-14 | 10.75 | 0 | 10.75 | 0 | 10.75 | 10.75 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | Up-gradation of infrastructure of Nishi Kumar Murasingh Para High School, Santirbazar, South Tripura | DM Gomati | NA | NA | NA | NA | 110.06 | 110.06 | 110.06 | Brownfield | 110.06 | SPA | 2011-12 | 109.79 | 0 | 109.79 | 0 | 99.05 | 99.05 | Completed | 0 | 0 | 10.74 | 0 | 0 | 0 | 0 | 0 | 0
185 | Kalacherra Junior Madrasa under Kadamtala Block, North Tripura. | DM N | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
186 | Dakshin Padmabil Naydrone Junior Madrasa under Panisagar Block, North Tripura. | DM N | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
187 | Ratacherra Junior Madrasa under Kumarghat Block, Unakoti. | DM U | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
188 | South Samrupur Junior Madrasa under Gournagar Block, Unakoti. | DM U | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
189 | Naba Santi Ganj Pathalia Junior Madrasa under Bishalgarh, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
190 | Ghaniamara Junior Madrasa under Bishalgarh, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
191 | Bastali Naljala Junior Madrasa under Bishalgarh Sub-Division, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
192 | Telkajla Islamia Junior Madrasa under Melaghar RD Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
193 | Adampur Hasania Junior Madrasa under Boxanagar RD Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
194 | Khaddya Khala Islamia Junior Madrasa under Kathalia RD Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
195 | Rabigopalpara Islamia Junior Madrasa under Melaghar R.D.Block, Sepahijala | DM W | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
196 | Karaliamura Junior Madrassa, Sonamura | DM SPJ | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
197 | Khedabari Islamia Junior Madrassa, Melaghar | DM SPJ | NA | NA | NA | NA | 15 | 15 | 15 | Greenfield | 15 | SPA | 2011-12 | 15 | 0 | 15 | NA | 15 | 0 | Completed | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0
198 | Renovation works at Padmapur HS for Kendriya Vidyalaya | DM North | NA | NA | NA | NA | 15.44 | 15.44 | 15.44 | Greenfield | 15.44 | SCA | 2014-15 | 15.44 | 0 | 15.44 | NA | 0 | 0 | Not started | 0 | 0 | 15.44 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 409.19 | 409.19 | 409.19 |  | 409.19 |  |  | 398.18 | 0 | 398.18 | 0 | 372 | 131.8 |  | 0 | 0 | 266.38 | 0 | 0 | 0 | 0 | 0

## Others
Sl No. | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund received in 2016 | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status | Fund lapsed | Revalidation required | Pending UC | Reallocation proposed | Refund to be proposed | Reallocation to be done | Reallocated | Drawn | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
167 | Taibandal H.S. School, Shipahijala Tripura | SDM SNM | NA | NA | NA | NA | 2.5 | 2.5 | 2.5 | Greenfield | 2.5 | SCA | 2014-15 | 2.5 | 0 | 2.5 | NA | 2.5 | 2.5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | Construction of 120 metre boundary wall of Manaipathar High School | I/S, Sonamura | NA | NA | NA | NA | 19 | 19 | 19 | Greenfield | 8.4 | SCA | 2014-15 | 8.4 | 0 | 8.4 | NA | 8.4 | 8.4 | Work completed first phase. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 120 meterboundary wall of telkajla H.S | I/S, Sonamura | NA | NA | NA | NA | 17.5 | 17.5 | 17.5 | Greenfield | 17.5 | SCA | 2014-15 | 17.5 | 0 | 17.5 | NA | 17.5 | 17.5 | Completed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | Procurement of furniture for Madrassa | DEE | NA | NA | NA | NA | 50 | 50 | 50 | Greenfield | 50 | SDS | 2015-16 | 50 | 0 | 50 | NA | 0 | 0 | In progree. Supply order issued | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0
199 | Purchase of land for NCI sonamura | SDM Sonamura | NA | NA | NA | NA | 230 | 230 | 230 | Greenfield | 230 | SCA | 2014-15 | 230 | 0 | 230 | NA | 186.375 | 186.375 | Completed | 0 | 0 | 43.625 | 0 | 0 | 0 | 0 | 0 | 0
200 | Infrastructure development of R K Mission Viveknagar & Agartala | RK Mission | NA | NA | NA | NA | 442.9 | 249.11 | 249.11 | Greenfield | 442.9 | NLCPR | 2013-14 | 249.11 | 0 | 249.11 | NA | 249.11 | 249.11 | Work in progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | Ramkrishna Pathshala J.B. School, West Tripura. | Eng Cell | NA | NA | NA | NA | 30 | 30 | 30 | Greenfield | 30 | SCA | 2014-15 | 30 | 0 | 30 | 0 | 0 | 0 | Work to be started soon. | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0
217 | Uniform grant to state government aided school | DSE | NA | NA | NA | NA | 55.22 | 55.22 | 55.22 | NA | 55.22 | SCA | 2013-14 | 55.22 | 21.25 | 33.97 | NA | 21.4 | 33.97 | Partially completed | 0 | 0 | 0 | 0 | 0 | 21.25 | 0 | 0 | 0
[7 empty] | 847.12 | 653.33 | 653.33 |  | 836.52 |  |  | 642.73 | 21.25 | 621.48 | 0 | 485.285 | 497.855 |  | 0 | 0 | 123.625 | 0 | 0 | 21.25 | 0 | 0

## NLCPR schools
| Sl. No | Name of project/School | Implementing Agency | Total rooms required as per Students strength | Existing Rooms available | No.of rooms taken up | Balance rooms required ('-' excess) | Project Cost (in lakhs) | Administrative Approval (in lakhs) | Expenditure Sanction (in lakhs) | Whether Greenfield or Brownfield ? | Project cost sanctioned by P&C | Scheme | Year | Fund received from FD | Fund drawn | Tendered value (in lakhs) | Expenditure incurred (in lakhs) | U.C. given | Physical status
209 | 36 | Algapur High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
210 | 37 | Lal Charra Colony High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
211 | 38 | Pabiya Charra High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
212 | 39 | Kalinagar High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
213 | 40 | Chantaibari High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
214 | 41 | Taranagar High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
215 | 42 | Jagatpur High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
216 | 43 | Pratapgarh High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
217 | 44 | Uttar Debendranagar High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
218 | 45 | Akhalia Charra High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
219 | 46 | Bagabassa High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
220 | 47 | Bijoygiri High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 18.74 | 18.74 | Completed
221 | 48 | Kathalia Charra H.S. School. | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 45.41 | 45.41 | Completed
222 | 49 | Durlabnarayan H.S. School. | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 45.41 | 45.41 | Completed
223 | 50 | Surendranagar H.S. School. | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 45.41 | 45.41 | Completed
224 | 51 | Badharghat H.S. School. | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 45.41 | 45.41 | Completed
225 | 52 | Chatakchari H.S. School. | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 45.41 | 45.41 | Completed
226 | 53 | Urmai H.S. School. | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 21.5 | 21.5 | Work above PL.
227 | 54 | Padmapur H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 27.69 | 27.69 | Centering and shuttring work is in progress for FF roof custed.
228 | 55 | Sribhumi H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 28.31 | 28.31 | Finishing work is in progress.
229 | 56 | Champaknagar H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 13.5 | 13.5 | 50% roof custing completed.
230 | 57 | Pitra H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 19.67 | 19.67 | Plastering work is in progress
231 | 58 | South Bagma H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 16.51 | 16.51 | Centering and shuttring work for roofing is in progress.
232 | 59 | Baikhora H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 16.51 | 16.51 | Raised upto roof level.
233 | 60 | East Kalabari H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 0 | 0 | Work will be started soon.
234 | 61 | Debdaru H.S. School | RD |  | NA | NA | NA | 45.41 | 45.41 | 45.41 | Greenfield | 45.41 | NLCPR | 2006-07 | 45.41 | 45.41 | NA | 0 | 0 | Finishing work is in progress.
235 | 62 | Dulogoang H.S. School | RD |  | NA | NA | NA | 23.9 | 23.9 | 23.9 | Greenfield | 23.9 | NLCPR | 2006-07 | 23.9 | 23.9 | NA | 14 | 14 | Roof slab cust completed.
236 | 63 | East Durjoynagar High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 5 | 5 | B/W upto lintel level & all column raised upto top beam level.
237 | 64 | Mirza Chandrapur High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 9.04 | 9.04 | Finishing work is going on.
238 | 65 | Jalemabari High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 9.04 | 9.04 | Roof custing work is in progress.
239 | 66 | Gokulnagar High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 9.04 | 9.04 | Finishing work is going on.
240 | 67 | Krishnagar Bhumihin High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 9.04 | 9.04 | Finishing work is going on.
241 | 68 | Uttar lalchari High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 9.04 | 9.04 | Raised upto PL
242 | 69 | Maharani High School. | RD |  | NA | NA | NA | 18.74 | 18.74 | 18.74 | Greenfield | 18.74 | NLCPR | 2006-07 | 18.74 | 18.74 | NA | 9.04 | 9.04 | Raised above PL